## Tuckerton Road West
Bridgeland Management District: Tuckerton Road West Connector
Fiscal Year and Quarter
Project Phase |  | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4 | 2022-1 | 2022-2 | 2022-3 | 2022-4 | 2023-1
TIP/STIP Amendments
AFA Execution
Procure Consultants
Kick Off
30%
60%
90%
95%/100%
NEPA
Utility Coordination/Relocation | Not Required
ROW Acquisition | Not Required
Letting
Construction
Implementation