## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | Kingsley - Clear Creek to BW 8 |  |  |  | Data populated/calculated based on inputs | Chambers | No
County | Harris |  |  |  |  | Fort Bend
Facility/Street Name | Kingsley Road/ Almeada School Rd |  |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  |  | Montgomery
Waller
Planning/Environmental | 4/2020 | 10/2021
Design | 12/2019 | 6/2021 | 1280 |  | 1560
Property/ROW Acquisition | 10/2021 | 10/2022 | 2520 |  | 360
Utility Relocation | 10/2022 | 4/2023 | 800 |  | 1200
Construction | 8/2023 | 12/2024 | 9244 |  | 11580
Federal Requested |  |  | 13844
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 3461 | 3461
Other |  |  | 0
Total Match |  |  | 3461
Total Project Cost ('000s) |  |  | 17305
0.2