## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | West Side / Westpark Connector Greenway |  |  | Data populated/calculated based on inputs | Chambers | No
County | Harris |  |  |  | Fort Bend
Facility/Street Name | Westpark Drive and Newcastle Drive |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  | Montgomery
Waller
Planning/Environmental | 2019-03-01 | 2019-09-01 | 86249.525
Design | 2019-09-01 | 2020-09-01 | 4605724.6376
Property/ROW Acquisition |  |  | 0
Utility Relocation |  |  | 0
Construction | 2020-10-01 | 2022-10-01 | 12861529.1753
Federal Requested |  |  | 17553503.338
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 4388375.8345
Other |  |  | 0
Total Match |  |  | 4388375.8345
Total Project Cost ('000s) |  |  | 21941879.1725

## WEST SIDE WESTPARK
Houston Parks Board TIP application
Conceptual Cost Estimate
2018-10-28
based on Beyond the Bayous implementation studies cost estimates
West Side/Westpark Connector Greenway
TIP Trail segments
| Along | Length (ft) | Type | Cost per linear foot | cost
| Metro Connection | 607.3671 | G1 | 330 | 200431.1398
| Westpark Greenway | 2116.2676 | G1 | 330 | 698368.2949
| Westpark Greenway | 5160.3882 | G2 | 160 | 825662.1158
| Westpark Greenway | 6355.965 | G1 | 330 | 2097468.4468
| N Centerpoint Row | 1944.388 | G1 | 330 | 641648.0511
| Centerpoint Row | 14580.5686 | G1 | 330 | 4811587.6441
| Braeswood Connection | 1968.955 | G1 | 330 | 649755.1491
|  | 6.1996 | Miles |  | 9924920.8415
G1: G type ROW with no need to remove rail
G2: G type ROW with no need to remove rail or pavement
TIP Intersections
| Crossing |  | Type |  | Cost_Tot
| Rampart |  | L |  | 5000
| Renwick |  | A |  | 60000
| Alder |  | L |  | 25000
| Chimney Rock |  | A |  | 60000
| Royalton |  | L |  | 25000
| South Rice |  | A |  | 60000
| W Loop Freeway |  | A |  | 50000
| W Loop Freeway |  | A |  | 50000
| Loop Central |  | L |  | 5000
| Newcastle |  | A |  | 50000
| Bridge over ditch |  | B |  | 800000
| Southwest Freeway |  | A |  | 300000
| Southwest Freeway |  | A |  | 300000
| Richmond |  | A |  | 300000
| Bissonnet |  | A |  | 300000
| Bellaire |  | A |  | 300000
| Rail |  | A |  | 50000
| Beachnut/Braeswood |  | A |  | 60000
| Bridge over ditch |  | B |  | 800000
| Rail |  | A |  | 50000
| Bridge over ditch |  | B |  | 800000
4450000
|  |  |  | subtotal intersections and segments | 14374920.8415
|  |  | 20% | Construction Contingency | 2874984.1683
|  |  |  | Construction Cost | 17249905.0098
|  |  | 19.5% | design costs | 3363731.4769
|  |  | 0.5% | plan/env | 86249.525
|  |  |  | Total project | 20699886.0118
|  |  | 6% | mgmt fee | 1241993.1607
|  |  |  | PROJECT TOTAL | 21941879.1725
|  |  |  | Planning / Environmental | 86249.525
|  |  |  | Design | 4605724.6376
|  |  |  | Construction | 17249905.0098
|  |  |  | check | 21941879.1725
|  |  |  | 20% match on construction | 4388375.8345
|  |  |  | Construction after match | 12861529.1753

## GREENWAY TYPE COSTS
Houston Parks Board TIP application
Conceptual Cost Estimate - Greenway Type Costs
2018-10-28
based on Beyond the Bayous implementation studies cost estimates
GREENWAY TYPE A
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Pavement Demolition | 15
Curb Demolition | 5
New Curbs | 20
Grading / Storm adjustment | 125
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 445
GREENWAY TYPE B
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Pavement Demolition | 29
Sidewalk Improvements | 80
New Pavement | 480
New Curbs | 80
Grading / Storm adjustment | 125
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 1074
GREENWAY TYPE C
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Pavement Demolition | 20
New Pavement | 400
New Curbs | 40 | new curbs one side
Grading / Storm adjustment | 50
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 790
GREENWAY TYPE D
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 340 | 2 x 10' wide concrete trails
Pavement Demolition | 56
New Pavement | 520
Grading / Storm adjustment | 125
Planting | 220 | 5'-6' planting both sides of trail x 2 trails
Total Cost per LF | 1261
GREENWAY TYPE E
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Parking Lot modification | 11
Retaining Wall | 75
Grading / Storm adjustment | 50
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 416
GREENWAY TYPE E1
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Parking Lot modification | 11
Grading / Storm adjustment | 50
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 341
GREENWAY TYPE F
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Pavement marking | 1 | paint
Intersection Transition | 16
Street Signage | 2
Total Cost per LF | 19
GREENWAY TYPE G1
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 170 | 10' wide concrete trail
Grading / Storm adjustment | 50
Planting | 110 | 5'-6' planting both sides of trail
Total Cost per LF | 330
GREENWAY TYPE H
Cost Per Linear Foot Breakdown
Item | Cost per LF | Notes
Concrete Trail | 340 | two 10' wide concrete trails
Pavement Marking | 15
Grading / Storm adjustment | 50
Planting | 220 | 5'-6' planting both sides of trail x 2 trails
Total Cost per LF | 625