## Form 1 Timeline
Handout 1 - Procurement Timeline Tool
Author: | Name |  | Date: | 2015-09-01
Instructions:
1. | Identify the Milestones. The model allows users to identify milestones based on the local government's procurement process. Enter milestones starting with the commencement of services back to the commencement of the procurement process.
2. | Estimate the Number of Calendar Days Between Milestones. Enter the number of calendar days from the milestone to the next milestone. |  |  |  | Number | Day
3. | Review the Tentative Schedule. Review the tentative schedule and adjust the number of calendar days between milestones as necessary. |  |  |  | 1 | Sunday
[5 empty] | 2 | Monday
| Milestone | Number of Calendars Days between Milestones | Tentative Schedule |  | 3 | Tuesday
|  |  | Date | Day | 4 | Wednesday
1 | Commencement of Services | NA | 2017-06-01 | Thursday | 5 | Thursday
2 | Approval of award by City Council | 200 | 2016-11-13 | Sunday | 6 | Friday
3 | Complete negotiations | 7 | 2016-11-06 | Sunday | 7 | Saturday
4 | Commence negotiatons | 90 | 2016-08-08 | Monday
5 | Complete evaluation of proposals | 7 | 2016-08-01 | Monday
6 | Initiate evaluation of proposals | 90 | 2016-05-03 | Tuesday
7 | Proposals due | 7 | 2016-04-26 | Tuesday
8 | Proposer questions deadline | 30 | 2016-03-27 | Sunday
9 | Pre-proposal meeting | 30 | 2016-02-26 | Friday
10 | Release RFP | 14 | 2016-02-12 | Friday
11 | Final draft of RFP | 30 | 2016-01-13 | Wednesday
12 | Complete review draft RFP by legal, purchasing, etc. | 30 | 2015-12-14 | Monday
13 | Draft RFP | 90 | 2015-09-15 | Tuesday
14 |  |  | NA | NA
15 |  |  | NA | NA
16 |  |  | NA | NA
17 |  |  | NA | NA
18 |  |  | NA | NA
19 |  |  | NA | NA
20 |  |  | NA | NA
Formulas:
Date: = IF(C13="","NA",[Date:, row above]-C13)