## Cover Page
Quarterly Progress Report
FY 20 Q1
Entity: HGAC
Contract No: 582-19-90201
Project Name: Cypress Creek WPP Development
Date Submitted: 12/12/19
Contractor Project Manager: Justin Bower
Approval Signature ____________________________ Date __1/9/20___
TCEQ Project Manager: Jessica Uramkin
Approval* Signature ____________________________Date
* The TCEQ Project Manager's signature indicates that the QPR is accepted as a project deliverable and also authorizes any changes in deliverable due dates requested in the Deliverables sheet. Approved due date changes should be inserted in the "Current Due Date" column in the next QPR.
1. When ready to submit the QPR to TCEQ, the Contractor Project Manager must date and sign the cover page with an electronic signature (i.e., scanned signature). Send the signed Excel document to the TCEQ Project Manager.
2. The TCEQ Project Manager will review and either: 1) Send back with comments or 2) approve, sign, date, and e-mail a scanned copy of the approved QPR to the Contractor Project Manager.
3. After addressing comments email the updated Excel document the TCEQ Project Manager, along with a new date next to the electronic signature.
4. The TCEQ Project Manager will sign, date, scan and send the approved QPR to the Contractor Project Manager. A final version of the Excel document will also be sent.

## Deliverables
If a deliverable is or will be late, a new due date must be proposed. If this is the case, a justification describing the circumstances necessitating the new due date must be provided.
ID# | Sub Task # | Deliverable | Current Due Date | Date Sent | Discussion of Progress Last Quarter (Delete info from prior QPRs, and leave blank if no progress occurred) | Proposed New Due Date
10029 | 1.2 | QPR (FY19Q1) | 2018-12-15 | NA | Contract initiated in Q2
10030 | 1.2 | QPR (FY19Q2) | 2019-03-15 | 2019-03-15
10031 | 1.2 | QPR (FY19Q3) | 2019-06-15 | 2019-06-14
10032 | 1.2 | QPR (FY19Q4) | 2019-09-15 | 2019-09-17
10033 | 1.2 | QPR (FY20Q1) | 2019-12-15 | 2019-12-12
10034 | 1.2 | QPR (FY20Q2) | 2020-03-15
10035 | 1.2 | QPR (FY20Q3) | 2020-06-15
10036 | 1.2 | QPR (FY20Q4) | 2020-09-15
10037 | 1.2 | QPR (FY21Q1) | 2020-12-15
10038 | 1.3 | Invoice (FY19Q1) | 2018-12-30 | NA | Contract initiated in Q2
10039 | 1.3 | Invoice (FY19Q2) | 2019-03-30 | 2019-03-30
10040 | 1.3 | Invoice (FY19Q3) | 2019-06-30 | 2019-06-27
10041 | 1.3 | Invoice (FY19Q4) | 2019-09-30 | 2019-09-30
10042 | 1.3 | Invoice (FY20Q1) | 2019-12-30 |  | To be sent under separate cover after close of quarter
10043 | 1.3 | Invoice (FY20Q2) | 2020-03-31
10044 | 1.3 | Invoice (FY20Q3) | 2020-06-30
10045 | 1.3 | Invoice (FY20Q4) | 2020-09-30
10046 | 1.3 | Invoice (FY21Q1)__Sept | 2020-10-30
10047 | 1.3 | Invoice (FY21Q1)_Oct | 2020-11-30
10048 | 1.3 | Invoice (FY21Q1)Nov | 2021-01-15
10050 | 1.4 | Conference Call (FY19Q2) | 2019-02-28 | Various
10051 | 1.4 | Conference Call (FY19Q3) | 2019-05-31 | 2019-04-29
10052 | 1.4 | Conference Call (FY19Q4) | 2019-08-31 | 2019-08-05
10053 | 1.4 | Conference Call (FY20Q1) | 2019-11-30 | 2020-01-09 | Call held 11/19 and notes to be submitted under separate cover.
10054 | 1.4 | Conference Call (FY20Q2) | 2020-02-29
10055 | 1.4 | Conference Call (FY20Q3) | 2020-05-31
10056 | 1.4 | Conference Call (FY20Q4) | 2020-08-31
10057 | 1.4 | Conference Call (FY21Q1) | 2020-11-30
10049 | 1.4 | Post-Award Mtg (Notes within 2 days of mtg) | 2018-10-31 | 2018-10-01
10058 | 1.5 | EPA Coordination Mtg (Upon Request) | 2020-11-30
10059 | 1.6 | Annual Report Article (If requested) | 2020-11-30
10060 | 1.7 | FY20 Annual Budget Update | 2020-01-31 |  | Awaiting request from TCEQ
10061 | 2.1 | QAPP Planning Mtg Notes | 2018-10-31 | 2018-10-01
10062 | 2.2 | Draft QAPP | 2019-01-31 | 2019-01-24
10063 | 2.2 | Final QAPP | TBD | 2019-06-13 | Date reflects final TCEQ approval.
10064 | 3.1 | Draft Data Analysis Summary Report, including documentation of data compilation and review and documentation of DMR/SSO analysis | 2020-01-03 |  | Modeling substantially completed and revised with stakeholder, draft will be completed by 12/31.
10065 | 3.1 | Final Data Analysis Summary Report, including documentation of data compilation and review and documentation of DMR/SSO analysis | 2020-11-30
10066 | 4.1 | Load duration curve update | 2020-01-03 |  | Draft report to be complete by 12/31, most modelling and revisions completed prior to end of quarter.
10067 | 4.2 | SELECT Update | 2020-01-03 |  | Draft report to be complete by 12/31, most modelling and revisions completed prior to end of quarter.
10068 | 4.3 | Draft Modeling Report | 2020-01-03 |  | Draft report to be complete by 12/31, most modelling and revisions completed prior to end of quarter.
10069 | 4.3 | Final Modeling Report | 2020-03-03 |  | Per discussion with TCEQ PM, to follow TCEQ review of report with adjusted date.
10070 | 5.1 | Draft Public Participation Plan | 2019-03-15 | 2019-03-15
10071 | 5.1 | Final Public Participation Plan | 2019-05-03 | 2019-05-01 | Date reflects final TCEQ approval.
10072 | 5.2 | Stakeholder Contact List (with QPRs) | 2020-11-30
10073 | 5.3 | Project Website | 2019-03-15 | 2019-03-15
10074 | 5.3 | Website Update (FY19Q3) | 2019-06-15 | 2019-06-14
10075 | 5.3 | Website Update (FY19Q4) | 2019-09-15 | 2019-09-15
10076 | 5.3 | Website Update (FY20Q1) | 2019-12-15 | 2019-12-12 | Materials for meetings added to Project Documents page. Announcements for meetings, survey, and other events hosted on front page.
10077 | 5.3 | Website Update (FY20Q2) | 2020-03-15
10078 | 5.3 | Website Update (FY20Q3) | 2020-06-15
10079 | 5.3 | Website Update (FY20Q4) | 2020-09-15
10080 | 5.3 | Website Update (FY21Q1) | 2020-12-15
10081 | 5.4 | Project Meeting (FY19Q1) | 2018-12-15
10082 | 5.4 | Project Meeting (FY19Q2) | 2019-03-15
10083 | 5.4 | Project Meeting (FY19Q3) | 2019-06-15 | 2019-06-14
10084 | 5.4 | Project Meeting (FY19Q4) | 2019-09-15 | 2019-07-26
10085 | 5.4 | Project Meeting (FY20Q1) | 2019-12-15 | 2020-01-09 | Partnership meetings were held 9/26 and 11/21, and Work Group Meetings were held in various dates during November.
10086 | 5.4 | Project Meeting (FY20Q2) | 2020-03-15
10087 | 5.4 | Project Meeting (FY20Q3) | 2020-06-15
10088 | 5.4 | Project Meeting (FY20Q4) | 2020-09-15
10089 | 5.4 | Project Meeting (FY21Q1) | 2020-12-15
10090 | 5.5 | Documentation of other meetings attended | 2019-03-15 | 2019-03-15
10091 | 5.5 | Documentation of other meetings attended | 2019-06-15 | 2019-06-14
10092 | 5.5 | Documentation of other meetings attended | 2019-09-15 | 2019-09-17
10093 | 5.5 | Documentation of other meetings attended | 2019-12-15 | 2019-12-12 | Contact documentation included in the narrative section of this QPR and in the stakeholder contact summary attached as a separate document.
10094 | 5.5 | Documentation of other meetings attended | 2020-03-15
10095 | 5.5 | Documentation of other meetings attended | 2020-06-15
10096 | 5.5 | Documentation of other meetings attended | 2020-09-15
10097 | 5.5 | Documentation of other meetings attended | 2020-12-15
10098 | 5.6 | Documentation of education and outreach events | 2019-09-15 | 2019-12-12
10099 | 5.6 | Documentation of education and outreach events | 2019-12-15 | 2019-12-12 | Outreach and education are reported in the Stakeholder contact summary included under separate cover.
10100 | 5.6 | Documentation of education and outreach events | 2020-03-15
10101 | 5.6 | Documentation of education and outreach events | 2020-06-15
10102 | 5.6 | FY19 Documentation of Partner Events Attended | 2019-11-30 | 2019-12-12 | Outreach and education are reported in the Stakeholder contact summary included under separate cover or forwarded separately for individual events.
10103 | 5.6 | FY20 Documentation of Partner Events Attended | 2020-11-30
10104 | 5.7 | Draft Stakeholder Outreach Task | 2020-09-30
10105 | 5.7 | Final Stakeholder Outreach Task | 2020-10-31
10107 | 6.1 | WPP Outline | 2019-05-31 | 2019-06-14
10106 | 6.1 | WPP Timeline | 2019-05-31 | 2019-05-01
10111 | 6.2 | Documentation of stakeholder approval of WPP | 2020-09-30
10112 | 6.2 | Draft WPP to EPA | 2020-10-15
10109 | 6.2 | Draft WPP to stakeholders and TCEQ | 2020-06-30
10114 | 6.2 | Final WPP to EPA | 2020-11-30
10113 | 6.2 | Response to comments from EPA | 2020-11-15
10110 | 6.2 | Response to comments from stakeholders and TCEQ | 2020-08-31
10108 | 6.2 | WPP Document Review Plan | 2019-04-30 | 2019-05-01
10117 | 6.3 | Documentation of dissemination of WPP and Executive Summary | 2020-11-30
10115 | 6.3 | Draft Executive Summary | 2020-09-30
10116 | 6.3 | Final Executive Summary | 2020-10-31
10118 | 7.1 | Final QPR as Final Report | 2020-12-15

## Narrative
Task/Issue | Additional Description of Quarterly Activities, Milestones, and Issues
1-Project Administration | H-GAC continued to administer the contract during this quarter. Quarterly communication with TCEQ PM was held during the quarter, along with other informal project discussion. Invoice for quarterly costs will be submitted by the due date.
2-Quality Assurance | H-GAC continued to implement the final approved QAPP. There were no issues with QAPP adherence in this quarter.
3 - Water Quality Data Acquisition and Evaluation | H-GAC completed data analyses, with the final report to be completed by early Q2 FY20.
4 – Modeling | H-GAC substantially completed modelling analyses, presented them for feedback to stakeholders and partners, and revised the modeling as needed. The final modeling report is expected in early Q2 FY20.
5 – Stakeholder Outreach | H-GAC held two formal Partnership meetings in the watershed. On 9/26 the Steering Committee was formed, and the Partnership discussed water quality issues and pollutant sources. On 11/21 the Partnership discussed bacteria sources and modeling results. Between the meetings stakeholders provided feedback at a series of Work Group meetings for Agriculture and Wildlife, and Human Sources. Good participation and active feedback were achieved across all meetings. H-GAC continued to work with local elected representatives on their interest in the project and with several partners (NRCS, KPC, et al.) on potential implementation efforts. H-GAC updated the website with project materials for meetings, notifications for other events, and a survey. H-GAC staff attended a number of outreach events in the project area, or serving project populations, including presentations to several conferences (greater detail is provided in the included Stakeholder Contact summary document). H-GAC attended regional and state meetings representing the project along with other watershed projects, including the Water and Sediment Quality subcommittee of the GBEP, H-GAC Natural Resources Advisory Council, etc. H-GAC staff discussed the project and outreach activities with a number of key stakeholders including Harris County Flood Control District, Bayou Land Conservancy, Katy Prairie Conservancy, Harris County Precinct 4 staff, Cypress Creek Flood Control Coalition, Texas Forest Service, et al. More information is available on the attached stakeholder contact documentation.
6 – WPP Development | Staff began completion of background information and modeling sections for TCEQ review and WPP inclusion.
7 – Final Report | No action was taken on this item
Note: The purpose of this sheet is to provide for an ongoing discussion of tasks to document overall progress and to raise any overall issues that don't relate to specific deliverables.
Note: Please address activities and issues related to contract amendments, budget revisions, and other administrative matters under Task 1.

## Budget
This tab is used for budget planning purposes. The TCEQ uses the information quarterly for program budget planning. It is important this form is completed to avoid rush requests from the TCEQ Project Manager. Section I tracks the current budget by fiscal year. This information is from the Annual Budget Update. This is a high-level overview of planned spending for each year of the project. Changes to fiscal year estimates are noted in Section III. After the current QPR is approved the new fiscal year estimates should be moved from Section III to Section I. Section II tracks the current fiscal year's invoicing. Include invoices that have been approved by TCEQ and estimates for upcoming invoices. Section III tracks changes in the fiscal year budgets. Changes may be an increase or a decrease in spending from original estimate. After the current QPR is approved the new fiscal year estimates should be moved from Section III to Section I.
Section I: Current Budget by FY |  |  |  | Section II: Current FY Quarterly Spending:
| Match | Federal |  |  | Match | Federal
FY19: | 32188.08 | 48282.12 |  | Q1: | 23109.89 | 34664.84
FY20: | 58008 | 87011 |  | Q2:
FY21 | 12627.92 | 18942.88 |  | Q3:
Q4:
Total: | 102824 | 154236 |  | Total: | 23109.89 | 34664.84
Section III: Has the total budget for this fiscal year changed? |  |  |  |  | No
If so, provide new budget by fiscal year estimates and justification for the change in the table below.
New Budget by FY:
| Match | Federal | Justification
FY19:
FY20:
FY21:
Totals: | 0 | 0

## QA_CA
Have any nonconformances occurred in the previous quarter? Yes/No |  |  |  | No
Add any nonconformances and the corresponding corrective actions to the Corrective Action Status Table below. Nonconformances must be communicated to the NPS Project Manager immediately via email and a Corrective Action Plan submitted within 14 days of the nonconformance occurring.
Corrective Action Status Table
Corrective Action # | Date Issued | Description of Deficiency | Action Taken | Date Closed

## Attachments
Please provide a listing of deliverables provided along with the QPR, and delete attachment references from prior quarters. Reference the "Deliverables Report" to get the Deliverable ID, Subtask #, and Deliverable Name.
Deliverable ID | Subtask # | Deliverable Name | Attachment File Name
10092 | 5.5 | Documentation of other meetings attended (stakeholder contact) | Stakeholder Contact Documentation Q1 FY20.docx