## Cover Page
Quarterly Progress Report
FY 20 Q3
Entity: HGAC
Contract No: 582-19-90201
Project Name: Cypress Creek WPP Development
Date Submitted: 6/15/20
Contractor Project Manager: Justin Bower
Approval Signature ____________________________ Date 7/29/20
TCEQ Project Manager: Jessica Uramkin (Emily Sanchez for JU)
Approval* Signature ____________________________Date 7/29/20
* The TCEQ Project Manager's signature indicates that the QPR is accepted as a project deliverable and also authorizes any changes in deliverable due dates requested in the Deliverables sheet. Approved due date changes should be inserted in the "Current Due Date" column in the next QPR.
1. When ready to submit the QPR to TCEQ, the Contractor Project Manager must date and sign the cover page with an electronic signature (i.e., scanned signature). Send the signed Excel document to the TCEQ Project Manager.
2. The TCEQ Project Manager will review and either: 1) Send back with comments or 2) approve, sign, date, and e-mail a scanned copy of the approved QPR to the Contractor Project Manager.
3. After addressing comments email the updated Excel document the TCEQ Project Manager, along with a new date next to the electronic signature.
4. The TCEQ Project Manager will sign, date, scan and send the approved QPR to the Contractor Project Manager. A final version of the Excel document will also be sent.

## Deliverables
If a deliverable is or will be late, a new due date must be proposed. If this is the case, a justification describing the circumstances necessitating the new due date must be provided.
ID# | Sub Task # | Deliverable | Current Due Date | Date Sent | Discussion of Progress Last Quarter (Delete info from prior QPRs, and leave blank if no progress occurred) | Proposed New Due Date
10029 | 1.2 | QPR (FY19Q1) | 2018-12-15 | NA | Contract initiated in Q2
10030 | 1.2 | QPR (FY19Q2) | 2019-03-15 | 2019-03-15
10031 | 1.2 | QPR (FY19Q3) | 2019-06-15 | 2019-06-14
10032 | 1.2 | QPR (FY19Q4) | 2019-09-15 | 2019-09-17
10033 | 1.2 | QPR (FY20Q1) | 2019-12-15 | 2019-12-12
| 1.2 | QPR (FY20Q2) | 2020-05-27 | 2020-05-27 | Issues due to COVID19 remote transition
10035 | 1.2 | QPR (FY20Q3) | 2020-06-15 | 2020-06-15
10036 | 1.2 | QPR (FY20Q4) | 2020-09-15
10037 | 1.2 | QPR (FY21Q1) | 2020-12-15
10038 | 1.3 | Invoice (FY19Q1) | 2018-12-30 | NA | Contract initiated in Q2
10039 | 1.3 | Invoice (FY19Q2) | 2019-03-30 | 2019-03-30
10040 | 1.3 | Invoice (FY19Q3) | 2019-06-30 | 2019-06-27
10041 | 1.3 | Invoice (FY19Q4) | 2019-09-30 | 2019-09-30
10042 | 1.3 | Invoice (FY20Q1) | 2019-12-30 | 2019-12-30
10043 | 1.3 | Invoice (FY20Q2) | 2020-03-31 | 2020-03-31
10044 | 1.3 | Invoice (FY20Q3) | 2020-06-30 | 2020-06-15
10045 | 1.3 | Invoice (FY20Q4) | 2020-09-30
10046 | 1.3 | Invoice (FY21Q1)__Sept | 2020-10-30
10047 | 1.3 | Invoice (FY21Q1)_Oct | 2020-11-30
10048 | 1.3 | Invoice (FY21Q1)Nov | 2021-01-15
10050 | 1.4 | Conference Call (FY19Q2) | 2019-02-28 | Various
10051 | 1.4 | Conference Call (FY19Q3) | 2019-05-31 | 2019-04-29
10052 | 1.4 | Conference Call (FY19Q4) | 2019-08-31 | 2019-08-05
10053 | 1.4 | Conference Call (FY20Q1) | 2019-11-30 | 2020-01-09
10054 | 1.4 | Conference Call (FY20Q2) | 2020-02-29 | 2020-02-19
10055 | 1.4 | Conference Call (FY20Q3) | 2020-05-31 | 2020-05-07
10056 | 1.4 | Conference Call (FY20Q4) | 2020-08-31
10057 | 1.4 | Conference Call (FY21Q1) | 2020-11-30
10049 | 1.4 | Post-Award Mtg (Notes within 2 days of mtg) | 2018-10-31 | 2018-10-01
10058 | 1.5 | EPA Coordination Mtg (Upon Request) | 2020-11-30
10059 | 1.6 | Annual Report Article (If requested) | 2020-11-30
10060 | 1.7 | FY20 Annual Budget Update | 2020-01-31 | 2020-02-19
10061 | 2.1 | QAPP Planning Mtg Notes | 2018-10-31 | 2018-10-01
10062 | 2.2 | Draft QAPP | 2019-01-31 | 2019-01-24
10063 | 2.2 | Final QAPP | TBD | 2019-06-13 | Date reflects final TCEQ approval.
10064 | 3.1 | Draft Data Analysis Summary Report, including documentation of data compilation and review and documentation of DMR/SSO analysis | 2020-01-03 | 2020-01-08
10065 | 3.1 | Final Data Analysis Summary Report, including documentation of data compilation and review and documentation of DMR/SSO analysis | 2020-11-30
10066 | 4.1 | Load duration curve update | 2020-01-03 | 2020-01-03
10067 | 4.2 | SELECT Update | 2020-01-03 | 2020-01-03
10068 | 4.3 | Draft Modeling Report | 2020-01-03 | 2020-03-09
10069 | 4.3 | Final Modeling Report | 2020-03-03 |  | comments received from TCEQ on 6/12, under revision currently. | 2020-06-26
10070 | 5.1 | Draft Public Participation Plan | 2019-03-15 | 2019-03-15
10071 | 5.1 | Final Public Participation Plan | 2019-05-03 | 2019-05-01
10072 | 5.2 | Stakeholder Contact List (with QPRs) | 2020-11-30
10073 | 5.3 | Project Website | 2019-03-15 | 2019-03-15
10074 | 5.3 | Website Update (FY19Q3) | 2019-06-15 | 2019-06-14
10075 | 5.3 | Website Update (FY19Q4) | 2019-09-15 | 2019-09-15
10076 | 5.3 | Website Update (FY20Q1) | 2019-12-15 | 2019-12-12
10077 | 5.3 | Website Update (FY20Q2) | 2020-03-15 | 2020-05-27
10078 | 5.3 | Website Update (FY20Q3) | 2020-06-15 | 2020-06-15 | See Narrative tab for details.
10079 | 5.3 | Website Update (FY20Q4) | 2020-09-15
10080 | 5.3 | Website Update (FY21Q1) | 2020-12-15
10081 | 5.4 | Project Meeting (FY19Q1) | 2018-12-15
10082 | 5.4 | Project Meeting (FY19Q2) | 2019-03-15
10083 | 5.4 | Project Meeting (FY19Q3) | 2019-06-15 | 2019-06-14
10084 | 5.4 | Project Meeting (FY19Q4) | 2019-09-15 | 2019-07-23
10085 | 5.4 | Project Meeting (FY20Q1) | 2019-12-15 | 2019-09-26
10086 | 5.4 | Project Meeting (FY20Q2) | 2020-03-15 | 2020-01-16
10087 | 5.4 | Project Meeting (FY20Q3) | 2020-06-15 | 2020-05-28 | Meetings held 3/12/20 (work groups) and 5/28/20 (Partnership)
10088 | 5.4 | Project Meeting (FY20Q4) | 2020-09-15
10089 | 5.4 | Project Meeting (FY21Q1) | 2020-12-15
10090 | 5.5 | Documentation of other meetings attended | 2019-03-15 | 2019-03-15
10091 | 5.5 | Documentation of other meetings attended | 2019-06-15 | 2019-06-14
10092 | 5.5 | Documentation of other meetings attended | 2019-09-15 | 2019-09-17
10093 | 5.5 | Documentation of other meetings attended | 2019-12-15 | 2019-12-12
10094 | 5.5 | Documentation of other meetings attended | 2020-03-15 | 2020-05-27
10095 | 5.5 | Documentation of other meetings attended | 2020-06-15 | 2020-06-15 | Contact documentation included in the narrative section of this QPR and in the stakeholder contact summary attached as a separate document.
10096 | 5.5 | Documentation of other meetings attended | 2020-09-15
10097 | 5.5 | Documentation of other meetings attended | 2020-12-15
10098 | 5.6 | Documentation of education and outreach events | 2019-09-15 | 2019-12-12
10099 | 5.6 | Documentation of education and outreach events | 2019-12-15 | 2019-12-12
10100 | 5.6 | Documentation of education and outreach events | 2020-03-15 | 2020-05-27
10101 | 5.6 | Documentation of education and outreach events | 2020-06-15 | 2020-06-15 | Outreach and education are reported in the Stakeholder contact summary included under separate cover.
10102 | 5.6 | FY19 Documentation of Partner Events Attended | 2019-11-30 | 2019-12-12
10103 | 5.6 | FY20 Documentation of Partner Events Attended | 2020-11-30
10104 | 5.7 | Draft Stakeholder Outreach Task | 2020-09-30
10105 | 5.7 | Final Stakeholder Outreach Task | 2020-10-31
10107 | 6.1 | WPP Outline | 2019-05-31 | 2019-06-14
10106 | 6.1 | WPP Timeline | 2019-05-31 | 2019-05-01
10111 | 6.2 | Documentation of stakeholder approval of WPP | 2020-09-30
10112 | 6.2 | Draft WPP to EPA | 2020-10-15
10109 | 6.2 | Draft WPP to stakeholders and TCEQ | 2020-06-30 |  | Requesting additional time due to COVID19 impact on outreach; meeting postponed from April to May, etc. | 2020-07-30
10114 | 6.2 | Final WPP to EPA | 2020-11-30
10113 | 6.2 | Response to comments from EPA | 2020-11-15
10110 | 6.2 | Response to comments from stakeholders and TCEQ | 2020-08-31
10108 | 6.2 | WPP Document Review Plan | 2019-04-30 | 2019-05-01
10117 | 6.3 | Documentation of dissemination of WPP and Executive Summary | 2020-11-30
10115 | 6.3 | Draft Executive Summary | 2020-09-30
10116 | 6.3 | Final Executive Summary | 2020-10-31
10118 | 7.1 | Final QPR as Final Report | 2020-12-15

## Narrative
Task/Issue | Additional Description of Quarterly Activities, Milestones, and Issues
1-Project Administration | H-GAC continued to administer the contract during this quarter. Quarterly communication with TCEQ PM was held during the quarter, along with other informal project discussion. Invoice for quarterly costs will be submitted by the due date. H-GAC staff discussed COVID19 impacts with TCEQ staff and moved as many elements virtual as possible.
2-Quality Assurance | H-GAC continued to implement the final approved QAPP. There were no issues with QAPP adherence in this quarter. The annual certification was completed in March.
3 - Water Quality Data Acquisition and Evaluation | H-GAC completed revisions to the data analyses report, and submitted the final reports to TCEQ.
4 – Modeling | H-GAC finalized modeling efforts. H-GAC staff are working with EPA and USACE on an external modeling effort for the watershed (no project funds or staff time are being used for modeling activities outside the QAPP; our time is going toward coordination with these partners and providing project data and guidance.)
5 – Stakeholder Outreach | H-GAC held one formal Partnership meeting in the watershed, and one set of work group meetings. On 3/12 the Partnership discussed bacteria solutions in work groups. On 5/28 the Partnership discussed wrapping up a list of potential solutions.Good participation and active feedback were achieved across all meetings, despite the early impacts of COVID19 in March, and the virtual meeting in May. H-GAC continued to work with local elected representatives on their interest in the project and with several partners (NRCS, KPC, et al.) on potential implementation efforts. H-GAC updated the website with project materials for meetings, notifications for other events, and a survey. H-GAC staff attended a number of outreach events in the project area, or serving project populations, including presentations to several meetings (greater detail is provided in the included Stakeholder Contact summary document). H-GAC attended regional and state meetings representing the project along with other watershed projects, including the Water and Sediment Quality subcommittee of the GBEP, H-GAC Natural Resources Advisory Council, etc. H-GAC staff discussed the project and outreach activities with a number of key stakeholders including Harris County Flood Control District, Bayou Land Conservancy, Katy Prairie Conservancy, Harris County Precinct 4 staff, Cypress Creek Flood Control Coalition, Texas Forest Service, et al. More information is available on the attached stakeholder contact documentation.
6 – WPP Development | Staff continued writing pieces of all sections for TCEQ review and WPP inclusion.
7 – Final Report | Staff discussed report formatting.
Note: The purpose of this sheet is to provide for an ongoing discussion of tasks to document overall progress and to raise any overall issues that don't relate to specific deliverables.
Note: Please address activities and issues related to contract amendments, budget revisions, and other administrative matters under Task 1.

## Budget
This tab is used for budget planning purposes. The TCEQ uses the information quarterly for program budget planning. It is important this form is completed to avoid rush requests from the TCEQ Project Manager. Section I tracks the current budget by fiscal year. This information is from the Annual Budget Update. This is a high-level overview of planned spending for each year of the project. Changes to fiscal year estimates are noted in Section III. After the current QPR is approved the new fiscal year estimates should be moved from Section III to Section I. Section II tracks the current fiscal year's invoicing. Include invoices that have been approved by TCEQ and estimates for upcoming invoices. Section III tracks changes in the fiscal year budgets. Changes may be an increase or a decrease in spending from original estimate. After the current QPR is approved the new fiscal year estimates should be moved from Section III to Section I.
Section I: Current Budget by FY |  |  |  | Section II: Current FY Quarterly Spending:
| Match | Federal |  |  | Match | Federal
FY19: | 32188.08 | 48282.12 |  | Q1: | 23109.89 | 34667.84 | reconciled with payment amounts 7/7/20
FY20: | 58008 | 87011 |  | Q2: | 16897.1 | 25345.65
FY21 | 12627.92 | 18942.88 |  | Q3: | 15893.81 | 23840.72
Q4:
Total: | 102824 | 154236 |  | Total: | 55900.8 | 83854.21
Section III: Has the total budget for this fiscal year changed? |  |  |  |  | No
If so, provide new budget by fiscal year estimates and justification for the change in the table below.
New Budget by FY:
| Match | Federal | Justification
FY19:
FY20:
FY21:
Totals: | 0 | 0

## QA_CA
Have any nonconformances occurred in the previous quarter? Yes/No |  |  |  | No
Add any nonconformances and the corresponding corrective actions to the Corrective Action Status Table below. Nonconformances must be communicated to the NPS Project Manager immediately via email and a Corrective Action Plan submitted within 14 days of the nonconformance occurring.
Corrective Action Status Table
Corrective Action # | Date Issued | Description of Deficiency | Action Taken | Date Closed

## Attachments
Please provide a listing of deliverables provided along with the QPR, and delete attachment references from prior quarters. Reference the "Deliverables Report" to get the Deliverable ID, Subtask #, and Deliverable Name.
Deliverable ID | Subtask # | Deliverable Name | Attachment File Name
10095 | 5.5 | Documentation of other meetings attended (stakeholder contact) | Stakeholder Contact Documentation Q3 FY20.docx