## SEMI-ANNUAL REPORT INSTRUCTIONS
SEMI-ANNUAL REPORT INSTRUCTIONS
The grant contract stipulates that the Council of Governments (COG) shall provide the TCEQ with a minimum of four written progress reports, to be submitted on a six-month basis, concerning its performance under the grant contract and documenting accomplishments of the grant-funded tasks and activities. Progress reports are due on the following schedule:
1st Half - 1st FY: | March 3oth (September -February)
2nd Half - 1st FY: | September 30th (March - August)
1st Half - 2nd FY: | March 30th (September - February)
2nd Half - 2nd FY: | December 31st (March - August) - Final
The attached reporting forms are provided for use by the COG to report on the conduct of grant-funded activities. The forms follow the major work tasks and requirements set forth in the grant contract. The COG may use another format, as long as the required information is included. Refer to the Administrative Guide for more detail instructions.
It is recommended that each COG submit a cumulative report, whereby the information entered for the previous reports will be left on the report file and included with the updated information entered for each new report. In this way, each subsequent report will contain a complete summary of grant-funded activities to date. This approach allows for the final report to serve not only as a report for the preceding six months, but also as a summary report for the entire grant period.
The Semi-Annual Report Form consists of four sections, as outlined below. In addition, there is an equipment log tab, and a tab for task and deliverables for the COG Managed Projects.
Cover Sheet - This should be completed with each report submitted. The report should be signed by an authorized official of the COG, e.g., one with signatory authority as identified in the grant application documents. Also, please note that the signature on the final report certifies that the COG has completed all of the tasks and deliverables required under the grant, and that the terms of the grant contract have been met. Any uncompleted requirements must be explained in the report.
Regional Coordination - This section covers the Regional Coordination activities set forth in the grant contract.
Regional Solid Waste Management Plan - This section will include the activities performed under the Regional Solid Waste Management Plan and Closed Landfill Inventory.
Implementation Project Selection - This section covers the Implementation Project Selection activities set forth in the grant contract and the Administrative Procedures. Note that space is provided to report on activities under the Private Industry Notification and Appeal Process.
Implementation Project and COG-Managed Administration - The final section is to be included once the COG awards its pass-through grants and/or is authorized to proceed with any COG-Managed Projects. This part of the report form provides for entry of summary information concerning the status of each project.

## COVER SHEET
REGIONAL SOLID WASTE GRANT SEMI-ANNUAL REPORT
HOUSTON-GALVESTON AREA COUNCIL - #16
FY 20/21
CONTRACT # : | 582-20-10214
Report #2 - March 1, 2020 - August 31, 2020 - Due September 30, 2020
Attachments:
Equipment Inventory Log (Required): | No
COG-Managed Project Task & Deliverables: | N/A
Signature/Title Certification
Title: | Manager
Typed/Printed Name: | Cheryl Mergo
Signature:
Date: | 2020-09-30
Program Completion Certification:
The submitting official certifies that to the best of his/her knowledge and belief, all tasks and deliverables required under the grant have been completed, except as noted and fully explained in the report, and the terms of the grant contract have been met.

## Regional Coordination
Regional Coordination
A. Solid Waste Advisory Committee.
Meetings to be held at least semi-annually. If a meeting is not held at least semi-annually, please provide an explanation.
1st Fiscal Year | Quarter | Meeting Dates
FY 20 | 1st (Sep, Oct, Nov) | 2019-10-23
| 2nd (Dec, Jan, Feb) | 2020-01-22
| 3rd (Mar, Apr, May) | 2020-04-22
| 4th (Jun, Jul, Aug) | 2020-07-22
2nd Fiscal Year | Quarter | Meeting Dates
FY 21 | 1st (Sep, Oct, Nov)
2nd (Dec, Jan, Feb)
3rd (Mar, Apr, May)
4th (Jun, Jul, Aug)
B. Technical Assistance
List summary information to reflect the level of technical assistance provided during the report period. Such information might include: number of telephone calls related to technical assistance; number of technical assistance meetings; number of other requests for assistance; and other information. Any inquiries regarding the Solid Waste Management Plan and Closed Landfill Inventory include them under the tab labeled RSWMP & Closed Landfill Inv.
1st Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 20 | First Half (September - February) Due March 31st
Ongoing - Usage of H-GAC's regional cooperative contract for HHW recycling. H-GAC has a contract with Stericycle.
Ongoing - Usage of H-GAC's regional cooperative contract for electronics recycling. H-GAC has a contract with CompuCycle.
Responded to 1 inquiry from consultants regarding the Closed Landfill Inventory.
Responded to 26 inquires from local governments regarding the grant application process.
9/5/2019: Provided information to a resident of Briargrove in Houston (Harris) regarding a recycling bin.
9/6/2019: Provided infomation to a resident of Katy (Harris) regarding disposing of a toilet.
9/9/2019: Provided information to a police agency wanting to start a Environmental Crime Unit/Task Force in Jefferson County (Beaumont)
9/9/2019: Provided information to a resident of Baytown (Chambers) regarding recycling cardboard boxes.
9/9/2019: Provided information to a resident of Spring (Harris) regarding tire disposal(recycling)
9/10/2019: Povided information to a resident of Harris County regarding VHS recycling.
9/10/2019: Provided information to a resident of Kemah (Galveston) regarding disposal of anti-freeze.
9/10/2019: Provided information to a resident of Galveston (Galveston) regarding disposal of paint.
9/16/2019: Provided information to a resident of Houston (Harris) regarding accepted items for curbside recycling.
9/16/2019: Provided information to a resident of Houston (Harris) regarding yard clippings disposal.
9/25/2019: Provided information to a resident of Spring (Harris) regarding a recycling bin.
9/26/2019: Provided information to a resident of Houston (Harris) regarding recycling electronics.
10/21/2019: Provided information to a resident of Houston (Harris) regarding recycling bin.
10/23/2019: Provided information to a resident of Houston (Harris) regarding recyling pick up.
10/28/2019: Provided information to a resident of Houston (Harris) regarding paint disposal.
10/29/2019: Povided information to a resident of Houston (Harris) regarding recycling pickup (lack of).
10/30/2019: Provided information to a resident of Santa Fe (Galveston) on the available options for properly disposing of household hazardous waste.
11/6/2019: Provided information to a resident of Cypress (Harris) regarding cardboard recycling.
11/21/2019: Provided information to a resident of League City (Galveston) regarding disposal of HHW.
11/21/2019: Provided information to a resident of Galveston (Galveston) regarding fluorescent bulb disposal/recycling.
12/2/2019: Provided information to a resident of Houston (Harris) regarding recycling pick up.
12/5/2019: Provided information to a resident of Houston (Harris) regarding tire disposal.
12/10/2019: Provided information to a resident of Houston (Harris) regarding styrofoam recycling.
12/10/2019: Provided information to a business of Houston (Harris) regarding oil recycling
12/12/2019: Provided information to a resident of Spring (Harris) regarding recycling electronics.
1/6/2020: Provided information to a resident of Harris regarding recycling.
1/8/2020: Provided information to a resident of Houston (Harris) regarding tire recycling.
1/8/2020: Provided information to a resident of Houston (Harris) regarding gasoline disposal.
2/7/2020: Provided information to a resident of Houston (Harris) regarding TV recycling.
2/8/2020: Privided information to a resident of Houston (Harris) regarding TV recycling.
2/24/2020: Provided information to a resident of Houston (Harris) regarding plastic recycling at apartment complex.
2/24/2020: Provided information to a resident of Harris County regarding recycling electronics.
FY 20 | Second Half (March - August ) Due September 30th
Ongoing - Usage of H-GAC's regional cooperative contract for HHW recycling. H-GAC has a contract with Stericycle.
Ongoing - H-GAC's regional cooperative contract for electronics recycling was expiring. H-GAC redid the "procurement" through the use of a Request for Proposals. Three (3) electronics recyclers submitted proposals for consideration. CompuCycle was again selected and the new contract is in place.
Responded to 9 inquiries from consultants regarding the Closed Landfill Inventory.
Responded to 17 inquires from local governments regarding the grant application process.
3/11/2020: Provided information to a resident of Harris County regarding recyling plastics.
3/12/2020: Provided information to a resident of Chambers County regarding incinerator.
4/2/2020: Provided information to a resident of Houston (Harris) regarding recyling.
4/8/2020: Provided information to a resident of Humble (Harris) regarding recycling.
4/13/2020: Provided information to a resident of Jersey Village (Harris) regarding recycling.
4/16/2020: Provided information to a resident of Humble(Harris) regarding dumping big furniture.
4/16/2020: Provided information to a resident of Houston (Harris) regarding recycling oil.
4/20/2020: Provided information to a resident of Harris regarding recycling plastic bottles.
4/29/2020: Provided information to a resident of Cypress (Harris) regarding TV disposal.
5/6/2020: Provided information to a business of Houston (Harris) how to dispose of oil.
5/14/2020: Provided information to a resident of Galveston regarding recyling HHW.
5/18/2020: Provided information to a resident of Pasadea (Harris) regarding heavy trash dumping.
5/20/20: Provided information to Montgomery County employee regarding website and recycling.
6/4/20: Provided information to a resident of Harris County regarding.
6/15/20: Provided information to a resident of Harris County regarding recycling projector TVs.
6/15/20: Provided information to a resident of Harris County regarding recycling styrofoam.
6/25/2020: Provided information to a resident of Harris County regarding recyling cardboard.
6/26/2020: Provided information to a resident of Harris County regarding recycling TV.
6/29/2020: Provided information to a resident of COH (Harris) regarding recycling bin.
6/30/2020: Provided information to a resident of Pasadena (Harris) regarding recycling electronic recycling.
6/30/2020: Provided information to a resident of Spring (Harris) regarding cardboard recycling.
7/7/2020: Provided information to a resident of Katy (Harris) regarding a recyling bin.
7/14/2020: Provided information to a resident of Houston (Harris) regarding recycling.
7/14/2020: Provided information to a resident of Houston (Harris) regarding recycling.
7/23/2020: Provided information to a resident of Beaumont Place (Harris) regarding trash.
7/23/2020: Provided information to a resident of Spring (Harris) regarding dumping a fryer.
8/4/2020: Privided information to a resident of Harris County regarding curbside recycling.
8/4/2020: Provided information to a resident of Harris County regarding paper recycling.
8/24/2020: Provided information to a resident of Harris County regarding recycling pickup.
8/25/2020: Provided information to a resident of Harris County regarding trash and recycling bins.
2nd Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 21 | First Half (September - February) Due March 31st
FY 21 | Second Half (March - August) Final Report Due October 31st
C. Regional Outreach, Education, & Training Activities
Serve as a central point of contact for waste management outreach, education, and training programs.
List major outreach, education, and training activities conducted. Include information on the results of each activity, such as the number of attendees and number of education/outreach items given out.
1st Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 20 | First Half (September - February) Due March 31st
Maintained Recycling Facebook Page (52 posts)
In February, H-GAC launched a program to provide weekly shareable Facebook posts on a different material for each month. The post each week focuses on reducing, reusing, recycling, or properly disposing of the material chosen for that month. Posts are also emailed to local government partners at the end of the month. Additionally, posts are converted to shareable Instagram and Twitter images and captions and are uploaded to the H-GAC website where they are available for download. http://www.h-gac.com/solid-waste-management/education-tools.aspx
Developed guidance for local government on weathering the downturn in recycling markets. Information was posted to the H-GAC website and can be found at http://www.h-gac.com/solid-waste-management/recycling/overcoming-recycling-challenges.aspx.
Ongoing - Held Trash Bash Steering Committee meetings. H-GAC is regional coordinator. September 18, 2019, November 20, 2019, January 15, 2020, and February 19, 2020
Regional Solid Waste Management Plan Update - internal meetings to discuss the plan were held on October 30, 2019, January 30, 2020, and February 26, 2020
Maintained Trash Bash Facebook Page (30 posts)
Participated in the City of Houston Long Range Solid Waste Plan Advisory Committee meetings: September 19, 2019 and September 24, 2019
Researched SEP funding to determine feasibility of providing solid waste funding to our local governments. Also researched possibility of H-GAC becoming a 3rd party administrator.
Researched and applied for EPA Trash Free Waters grant in coordination with NCTCOG. Funds would be used to address illegal dumping and litter. The grant was awarded.
Research was begun by staff to determine which local governments offer curbside recycling.
Research was conducted by a temp to determine the appropriate contact in each county and city for solid waste management.
9/17/2019: Held a workshop on Completing the Solid Waste Grant Application. (28 attended)
11/21/2019: Held a workshop on Challenging Waste Streams. (34 attended)
2/6/2020: Presented at the Natural Resources Advisory Committee on the current efforts and programs of the solid waste program. (22 in attendance)
2/7/2020: Presented to the senior citizens group at the Crosby Community Center on recycling. (15 attended)
FY 20 | Second Half (March - August ) Due September 30th
H-GAC continued the program to provide weekly shareable Facebook posts on a different material for each month that was launched in February 2020. The post each week focuses on reducing, reusing, recycling, or properly disposing of the material chosen for that month. Posts are also emailed to local government partners at the end of the month. During the second half of the fiscal year H-GAC posted 38 posts and shares on the H-GAC Recycling Facebook page. Additionally, posts are converted to shareable Instagram and Twitter images and captions and are uploaded to the H-GAC website where they are available for download. http://www.h-gac.com/solid-waste-management/education-tools.aspx. During this quarter 12 Instagram images/captions and 12 Twitter images/captions were posted to the H-GAC website.
Periodic updates to the H-GAC website, including adding a link to the EPA Disaster Debris Recovery Tool.
Conducted a survey in late March and early April to determine the impact COVID-19 was having on waste and recycling in the region and opportunities to mitigate damage. Eighteen (18) responses were received in the four (4) days the survey was live.
Trash Bash had been scheduled for March 28, 2020. Due to the pandemic it was cancelled.
Maintained Trash Bash Facebook Page (10 posts)
Participated in the City of Houston Long Range Solid Waste Plan Advisory Committee meetings: June 29, 2020 and July 15, 2020
Participated in the TARC Regional Solid Waste Management Plan Workgroup calls on March 26, 2020 and June 17, 2020.
| 3/5/2020: Held a workshop as part of our Solid Waste Workshop Series. The topic was Environmental Enforcement. (49 attended) | Solid Waste Workshop Series - Environmental Enforcement
| 3/19/2020: Held a webinar on how to complete the online Solid Waste Grant Application. (20 attended) | Solid Waste Grant Application Workshop
| 5/7/2020: Gave a short presentation at the Natural Resource Advisory Committee, an H-GAC Board appointed committee, on the current and upoming projects of the Solid Waste Program. (33 were in attendance) | Presentation at NRAC
| 5/21/2020: Held a webinar as part of our Solid Waste Workshop Series. The topic was Recycling. (43 attended) | Solid Waste Workshop Series - Recycling Webinar
| 7/30/2020: Held a webinar for our FY20 Solid Waste Grantees to train them on the required reporting of the implementation grants and the rules of the grant program. This is a required training, although they are allowed to make it up another day. (29 attended) | Solid Waste Grantee Training
| 8/6/2020: Gave a short presentation at the Natural Resource Advisory Committee, an H-GAC Board appointed committee, on the current and upoming projects of the Solid Waste Program. (34 were in attendance) | Presentation at NRAC
| 8/26/2020: Held a webinar as part of our Solid Waste Workshop Series. The topic was Waste Diversion. (29 attended) | Solid Waste Workshop Series - Waste Diversion
2nd Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 21 | First Half (September - February) Due March 31st
FY 21 | Second Half (March - August) Final Report Due December 31st
D. Training and Meetings
List major staff training activities, conference/seminar attendance, TCEQ meetings and workshops, and similar activities not reported under a separate work task. Do not list SWAC meetings.
Conference/Meeting/Training/Workshop - Location |  | Date (s)
TARC Bi-Annual Staff Training, Austin, Texas |  | 2019-09-11
Webinar: Increasing MRF Efficiency: How to Minimize Contamination by Preventing it at Your Front Door |  | 2019-09-17
STAR Summit, San Antonio, Texas |  | 10/7/2019 - 10/9/2019
Webinar: After the Storm: Equitable Recovery and Resilient Adaptations |  | 2019-10-09
TCEQ MSW Advisory Council quarterly meeting, Austin, Texas |  | 2019-10-10
Webinar: How to Use HGACBuy's Contracts for FEMA |  | 2019-11-12
TCEQ MSW Advisory Council quarterly meeting, Austin, Texas |  | 2020-01-16
TARC Bi-Annual Staff Training, Austin, Texas |  | 2020-02-05
Webinar: ReUse in the Entertainment Industry |  | 2020-02-27
Webinar: Rethinking and Replacing the Three R's - Creating a Culture of Composters and Recyclers at Fossil Rim Wildlife Center in 2020 |  | 2020-03-31
Webinar: Covid-19 and its Impacts on Recycling |  | 2020-03-31
Webinar: COVID-19: Industry Outlook |  | 2020-04-02
Webinar: EPA Trash Free |  | 2020-04-15
Webinar: Recycling Industry and the Supply Chain During a Pandemic |  | 2020-04-16
Webinar: Effective Disaster Mitigation Project |  | 2020-05-14
Webinar: STAR 3rd Annual Texas Resuse Tour |  | 2020-06-16
Webinar: Texas Clean and Healthy Meeting - East Gulf Region |  | 2020-06-24
Resource Recycling Webinar: Ask the Giants |  | 2020-07-08
TCEQ MSW Advisory Council quarterly meeting (online only) |  | 2020-07-09
STAR North Texas Webinar: Impacts of Covid-19 on North Texas Recycling Programs |  | 2020-07-16
Progress Report Review Training for Staff |  | 2020-07-27
Resource Recycling Webinar: What to Expect from Domestic Paper Markets |  | 2020-07-29
STAR Central Texas Council: Recycling Processors |  | 2020-08-12
Webinar: How to Use Regional Equity Tool for Project Planning (Pramod's thing) |  | 2020-08-20
Webinar: Exploring the Connection Between Covid-19, Waste Management, Recycling, and Sustainability |  | 2020-08-25
Resource Recycling Webinar: Measurement Matters: How Do We Measure Now? |  | 2020-08-26
E. Regional Information Resource Center
Maintain a resource center with a collection of regional solid waste information and reference materials.
List summary information on the use of the resource center, such as the number of requests for information and materials.
1st Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 20 | First Half (September - February) Due March 31st
10/25/2019: 100 kids' recycling activity books and 100 stickers provided to the City of Willis to be handed out at upcoming events.
11/4/2019: 175 kids' recycling activity books and 150 stickers provided to Montgomery County to be handed out to those visiting the recycling drop-off facility.
11/20/2019: 300 kids' recycling activity books and 300 stickers provided to Alief Petrosky Elementary to be handed out to students.
1/8/2020: 40 kids' recycling activity books and 50 stickers provided to the City of West University Place to be handed out at upcoming events.
2/3/2020: 400 kids' recycling activity books, 400 stickers, and 400 Earth911 magnets provided to the City of Houston to be handed out at an event.
2/7/2020: 11 Earth911 magnets distributed during a presentation on recycling at the Crosby Community Center.
FY 20 | Second Half (March - August ) Due September 30th
2nd Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 21 | First Half (September - February) Due March 31st
FY 21 | Second Half (March - August) Final Report Due December 31st
F. Pre-Application Review Process
Respond to requests by prospective applicants for an MSW permit or registration for the COG to provide a preliminary evaluation of the conformance with the regional solid waste management plan.
List all proposed facilities evaluated, meetings held, and a brief summary of the results of the meetings and evaluations.
1st Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 20 | First Half (September - February) Due March 31st
No activity for this reporting period.
FY 20 | Second Half (March - August ) Due September 30th
No activity for this reporting period.
2nd Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 21 | First Half (September - February) Due March 31st
FY 21 | Second Half (March - August) Final Report Due December 31st
G. MSW Facility Application Review.
Review applications for solid waste management facilities for conformance with the regional solid waste management plan.
List permit and registration applications reviewed and the determination made by the COG (i.e., is or is not consistent with the regional plan). Submit the letter that was sent to TCEQ that indicates the entity was in conformance.
1st Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 20 | First Half (September - February) Due March 31st
Staff reviewed the Seabreeze Environmental Landfill located in Brazoria County. During the September 17, 2019 Plans and Projects Review Committee and Board of Directors meetings staff gave a presentation to summarize the facility plans and comments received from local governments. The facility was found to be consistent with comments with plans, policies, and H-GAC review criteria.
Staff reviewed the Ralston Road Landfill located in Harris County. During the September 17, 2019 Plans and Projects Review Committee and Board of Directors meetings staff gave a presentation to summarize the facility plans and comments received from local governments. The facility was found to be consistent with comments with plans, policies, and H-GAC review criteria.
FY 20 | Second Half (March - August ) Due September 30th
Staff reviewed the JSI Houston Transfer Station Inc. (R&J Transfer Station) located in Harris County. As part of the review process a site visit was conducted on April 24, 2020. During the June 16, 2020 Plans and Projects Review Committee and Board of Directors meetings staff gave a presentation to summarize the facility plans and comments received from local governments. The facility was found to be consistent with comments with plans, policies, and H-GAC review criteria.
2nd Fiscal Year (this is reported twice a year, the first and second half of each fiscal year).
FY 21 | First Half (September - February) Due March 31st
FY 21 | Second Half (March - August) Final Report Due December 31st
Note on B6: Once the FY is selected it will auto-populate the other FY's below from Forms A - G.
Note on B11: Once the FY is selected it will auto-populate the other FY's below from Forms A - G.
Note on B18: This field will auto-populate when the FY from section A above is selected.
Note on B56: This field will auto-populate when the FY from section A above is selected.
Note on B93: This field will auto-populate when the FY from section A above is selected.
Note on B109: This field will auto-populate when the FY from section A above is selected.
Note on B129: This field will auto-populate when the FY from section A above is selected.
Note on B146: This field will auto-populate when the FY from section A above is selected
Note on B166: This field will auto-populate when the FY from section A above is selected.
Note on B182: This field will auto-populate when the FY from section A above is selected
Note on B234: This field will auto-populate when the FY from section A above is selected.
Note on B249: This field will auto-populate when the FY from section A above is selected.
Note on B266: This field will auto-populate when the FY from section A above is selected.
Note on B282: This field will auto-populate when the FY from section A above is selected.
Note on B303: This field will auto-populate when the FY from section A above is selected.
Note on B318: This field will auto-populate when the FY from section A above is selected.
Note on B335: This field will auto-populate when the FY from section A above is selected.
Note on B351: This field will auto-populate when the FY from section A above is selected.
Note on B372: This field will auto-populate when the FY from section A above is selected.
Note on B387: This field will auto-populate when the FY from section A above is selected.
Note on B404: This field will auto-populate when the FY from section A above is selected.
Note on B420: This field will auto-populate when the FY from section A above is selected.

## RSWMP & Closed Landfill Inv.
Regional Solid Waste Management Plan And Closed Landfill Inventory
Regional Solid Waste Management Plan
Provide Any Updates In the Spaces Below. Additional spaces and expanded cells is an option, if needed.
Report 1: | N/A
Report 2: | H-GAC has begun the process of updating the plan. A steering committee has been formed and has met five (5) times. There are six (6) members of the Solid Waste Advisory Committee on the plan steering committee. The committee meetings were held on March 4, 2020, May 28, 2020, June 18, 2020, July 15, 2020, and August 5, 2020. Staff also held internal meetings on March 25, 2020 and April 14, 2020 to discuss the update process. The committee has worked on developing/updating the goals and objectives and has discussed data collection. Additionally, the committee has worked on a survey that was sent out to local governments to collect information regarding their solid waste related programs. The survey was distributed and to date twenty-one (21) cities and counties have responded to the survey.
Report 3:
Report 4:
Expected Completion Date: | 2021-08-31
Comments: Suggested comments include the number of inquiries related to the Solid Waste Management Plan; number of technical assistance, etc.
Report 1: | N/A
Report 2: | N/A
Report 3:
Report 4:
Closed Landfill Inventory
Comments: Suggested comments include the number of inquiries related to the Closed Landfill Inventory; number of technical assistance; copies mailed; etc.
Report 1: | We received one (1) inquiry during the first quarter. Requested files were sent via email.
Report 2: | We received nine (9) inquiries during the second quarter. Requested files were sent via email.
Report 3:
Report 4:
Provide Any Updates In the Spaces Below.
Report 1: | N/A
Report 2: | N/A
Report 3:
Report 4:

## IPS Project Selection
Implementation and COG Managed Project Selection Process
A. Project Review and Selection (First Fiscal Year)
Conduct a request for applications, review, and selection process.
1st Fiscal Year | Project Selection Process | Dates /Other Information
FY 20 | Competitive Application Period: | 9/4/2019 - 10/17/2019
| -Direct Notice to all eligible applicants: | 8/26/2019 & 9/4/2019
| -Private Industry Notice: | 9/5/2019 & 10/17/2019
-Other Notice (specify):
| # of Applications Received: | 28
| SWAC Ranking and/or Review and Selection: | 11/4-5/2019 scoring; 11/11/2019 SWAC review
| Governing Body Final Selection: | 2019-12-17
| Project Summaries Submitted to TCEQ: | 2020-01-13
Additional Projects: funded after the initial project selection process, if applicable: |  | Dates
SWAC Ranking and/or Review and Selection:
Governing Body Final Selection:
Project Summaries Submitted to TCEQ:
Additional Projects: funded after the initial project selection process, if applicable: |  | Dates
SWAC Ranking and/or Review and Selection:
Governing Body Final Selection:
Project Summaries Submitted to TCEQ:
B. Project Review and Selection (Second Fiscal Year, if applicable)
Conduct a request for applications, review, and selection process.
2nd Fiscal Year | Project Selection Process | Dates /Other Information
FY 21 | Competitive Application Period: | 3/3/2020 - 4/16/2020
| -Direct Notice to all eligible applicants: | 2/11/2020, 3/3/2020, & 3/17/2020
| -Private Industry Notice: | 3/3/2020 & 4/17/2020
-Other Notice (specify):
| # of Applications Received: | 12
| SWAC Ranking and/or Review and Selection: | 5/5/2020 scoring, 5/12/2020 SWAC review
| Governing Body Final Selection: | 2020-06-16
| Project Summaries Submitted to TCEQ: | 2020-06-17
Additional Projects: funded after the initial project selection process, if applicable: |  | Dates
SWAC Ranking and/or Review and Selection:
Governing Body Final Selection:
Project Summaries Submitted to TCEQ:
Additional Projects: funded after the initial project selection process, if applicable: |  | Dates
SWAC Ranking and/or Review and Selection:
Governing Body Final Selection:
Project Summaries Submitted to TCEQ:
C. Private Industry Notification and Appeal Process.
List of Private Service Providers Updated by COG (dates): This should include the beginning date of the biennium, and then updated throughout the contract term.
List the instances where a private service provider opposed a project, and explain actions/decisions by the COG. Include information on the status of pending decisions and appeals.
Summarize other activities:
D. Additional Implementation Project Administration Activities.
List additional implementation project administration activities conducted to date.
If applicable, include information on major meetings held, assistance and review provided to grant recipients, and other important activities. Include dates, locations, and other applicable information.

## IPS_COG Managed Project Admin
Implementation Project and COG - Managed Administration
Pass-Through Grant and COG Managed Summary
List all Pass-Through Grants, and COG-Managed Projects awarded or authorized to date. The COG should maintain copies of all reports, plans, brochures, and other information or materials developed as part of the project.
Note: A COG-Managed Project task and deliverables list is required, see tab "Attach-CMP-Task-Deliverables" included in this workbook for your use, or you can submit a separate document that provides the required information.
TCEQ Project # | Grant Recipient and Project Description | Expected Completion Date | Percent (%) Complete | Progress Report / Remarks (required)
20-16-01 | City of Sugar Land - ISD Recycling Education | 2021-06-30 | 0% | Still working to get the contract signed. The City is uncomfortable with some sections and we are working to find a solution.
20-16-02 | City of Alvin - Transportation of Recycled Materials | 2021-06-30 | 15% | Contract has been fully executed. Six commercial recycling bins have been ordered and will be installed for the public to use beginning October 1, 2020.
20-16-03 | Austin County - HHW & Electronic Collection Event | 2021-06-30 | 15% | Contract has been fully executed. The location for the collection event has been secured and the event will be held in the spring. Flyers for the event have been designed and just need to be updated with the selected date.
20-16-04 | Walker County - Tire Collection Event | 2021-06-30 | 50% | Contract has been fully executed. The County held the first of two scrap tire collection events in March. The second had been planned for April in another part of the County, but due to COVID-19 it was postponed.
20-16-05 | Galveston County - HHW & Electronic Collection Event | 2021-06-30 | 10% | Contract has been fully executed. The County had originally planned to hold the collection event at the Dog Track, but since the property is being sold they will likely need to go with their second choice location, for which they have a tentative agreement in place. The County has contracts in place with the chosen vendors. The event is planned for early 2021.
20-16-06 | City of Pasadena - Local Enforcement Server | 2021-06-30 | 5% | Contract has been fully executed. The server has not yet been purchased.
20-16-07 | City of Bay City - Restore Recycling Trailers | 2021-06-30 | 25% | Contract has been fully executed. The City has obtained quotes for the work to be performed on the trailers and has selected the contractor. They are awaiting approval on the purchase order for the contractor.
20-16-08 | Walker County - Composting & Recycling Education | 2021-06-30 | 20% | Contract has been fully executed. Materials for the compost area were purchased and construction has completed.
20-16-09 | Montgomery County - Recycling Compactor & Containers | 2021-06-30 | 50% | Contract has been fully executed. The County has purchased two compactors and two containers. All other purchases have not yet been made.
20-16-10 | City of Houston - Local Enforcement Equipment (Vehicle and Server) | 2021-06-30 | 5% | There were some concerns the City had with the initial contract, but they have been remedied and the contract has been fully executed. The city was awarded additional funds during the second round of grant selection and the contract change order for the additional funds is being processed. Due to the delay in getting the initial contract signed no work has been completed by the grantee.
20-16-11 | City of Houston - Curbside Recycling Education | 2021-06-30 | 5% | There were some concerns the City had with the initial contract, but they have been remedied and the contract has been fully executed.
20-16-12 | City of Hitchcock - Local Enforcement Officer, Vehicle, & Equipment | 2021-06-30 | 37% | Contract has been fully executed. The new Environmental Enforcement Officer was hired and began in June 2020.
21-16-01 | Colorado County - HHW, Electronics, & Tire Collection Event | 2021-06-30 | 5% | Contract has been fully executed. Grant period began on September 1, 2020.
21-16-02 | Austin County - Tire Collection Events | 2021-06-30 | 5% | Contract has been fully executed. Grant period began on September 1, 2020.
21-16-03 | City of El Campo - Bale Clamp for Recycling Center | 2021-06-30 | 5% | Grant period began on September 1, 2020.
21-16-04 | City of Pearland - Recycling Facility Equipment | 2021-06-30 | 5% | Contract has been fully executed. Grant period began on September 1, 2020.
21-16-05 | City of Houston - Forklift for HHW Facility | 2021-06-30 | 5% | Grant period began on September 1, 2020.
21-16-06 | Brazoria County - Tire Collection Event | 2021-06-30 | 5% | Contract has been fully executed. Grant period began on September 1, 2020.
21-16-07 | City of Palacios - Enhance Recycling Facility/Baler | 2021-06-30 | 5% | Contract has been fully executed. Grant period began on September 1, 2020.
21-16-08 | Galveston County - Local Enforcement Cameras | 2021-06-30 | 5% | Contract has been fully executed. Grant period began on September 1, 2020.
21-16-09 | City of Bellaire - HHW Vouchers | 2021-06-30 | 5% | Grant period began on September 1, 2020.
21-16-10 | City of Pattison - HHW Collection Event/Education | 2021-06-30 | 5% | Grant period began on September 1, 2020.
21-16-11 | Fort Bend County - Bulb Eater Machine | 2021-06-30 | 5% | Contract has been fully executed. Grant period began on September 1, 2020.
21-16-12 | City of Houston - Phone App - Misc. Education | 2021-06-30 | 5% | Grant period began on September 1, 2020.
Project Site Visits Conducted
Use this form to track and report the required one site visit per funded entity. Include equipment inventory ID #’s if appropriate.
TCEQ Project # | Date Of Visit |  | Progress Report / Remarks (required)

## Attach-CMP-Task-Deliverables
COG-Managed Project Tasks and Deliverables
HOUSTON-GALVESTON AREA COUNCIL - #16
FY 20/21
State the overall goal of the project in the space provided below:
Use this space to type in the overall goal.
Task 1.
Use this space to type in task/scope of work statement
Deliverable:
A. Percent % Completed:
B. Activities Conducted to Date:
C. Major activities remaining to complete the task:
D. Estimated Completion Date:
E. Comments (Explain any problems encountered in conducting the overall project. Provide other information that may be helpful in understanding the status of the project):
Task 2.
Use this space to type in task/scope of work statement
Deliverable:
A. Percent % Completed:
B. Activities Conducted to Date:
C. Major activities remaining to complete the task:
D. Estimated Completion Date:
E. Comments (Explain any problems encountered in conducting the overall project. Provide other information that may be helpful in understanding the status of the project):
Task 3.
Use this space to type in task/scope of work statement
Deliverable:
A. Percent % Completed:
B. Activities Conducted to Date:
C. Major activities remaining to complete the task:
D. Estimated Completion Date:
E. Comments (Explain any problems encountered in conducting the overall project. Provide other information that may be helpful in understanding the status of the project):
Task 4.
Use this space to type in task/scope of work statement
Deliverable:
A. Percent % Completed:
B. Activities Conducted to Date:
C. Major activities remaining to complete the task:
D. Estimated Completion Date:
E. Comments (Explain any problems encountered in conducting the overall project. Provide other information that may be helpful in understanding the status of the project):
Task 5.
Use this space to type in task/scope of work statement
Deliverable:
A. Percent % Completed:
B. Activities Conducted to Date:
C. Major activities remaining to complete the task:
D. Estimated Completion Date:
E. Comments (Explain any problems encountered in conducting the overall project. Provide other information that may be helpful in understanding the status of the project):
Task 6.
Use this space to type in task/scope of work statement
Deliverable:
A. Percent % Completed:
B. Activities Conducted to Date:
C. Major activities remaining to complete the task:
D. Estimated Completion Date:
E. Comments (Explain any problems encountered in conducting the overall project. Provide other information that may be helpful in understanding the status of the project):

## Attach-Equipment Log
Regional Solid Waste Grant Semi-Annual Report - Equipment Log
HOUSTON-GALVESTON AREA COUNCIL - #16
FY 20/21
Date: |  |  | Insert Date Here
Grant # | Subrecipient | Project Category (use the drop down menu by clicking in the box below to select the category) | Equipment Description | Serial # | Cost | Purchase Date | Still in use / disposition (use the drop down menu by clicking in the box below to select your answer)
Note: See Admin Guide for more detail instructions for maintaining this equipment log.

## CODES (hidden)
Select COG Name And Number From The Drop Down Menu By Clicking In This Box | Select Biennium From the Drop Down Menu By Clicking In This Box
PANHANDLE REGIONAL PLANNING COMMISSION - #1 | FY 20/21
SOUTH PLAINS ASSOCIATION OF GOVERNMENTS - #2 | FY 22/23
NORTEX REGIONAL PLANNING COMMISSION - #3
NORTH CENTRAL TEXAS COUNCIL OF GOVERNMENTS - #4 | Select 1st FY from the Biennium From the Drop Down Menu By Clicking In This Box
ARK-TEX COUNCIL OF GOVERNMENTS - #5 | Select 2nd FY from the Biennium From the Drop Down Menu By Clicking In This Box
EAST TEXAS COUNCIL OF GOVERNMENTS - #6 | FY 20
WEST CENTRAL TEXAS COUNCIL OF GOVERNMENTS - #7 | FY 21
RIO GRANDE COUNCIL OF GOVERNMENTS - #8 | FY 22
PERMIAN BASIN REGIONAL PLANNING COMMISSION - #9 | FY 23
CONCHO VALLEY COUNCIL OF GOVERNMENTS - #10
HEART OF TEXAS COUNCIL OF GOVERNMENTS - #11 | Select Appropriate FY From the Drop Down Menu By Clicking In This Box
CAPITAL AREA COUNCIL OF GOVERNMENTS - #12 | FY 20
BRAZOS VALLEY COUNCIL OF GOVERNMENTS - #13 | FY 21
DEEP EAST TEXAS COUNCIL OF GOVERNMENTS - #14 | FY 22
SOUTH EAST TEXAS REGIONAL PLANNING COMMISSION - #15 | FY 23
HOUSTON-GALVESTON AREA COUNCIL - #16
GOLDEN CRESCENT REGIONAL PLANNING COMMISSION - #17
ALAMO AREA COUNCIL OF GOVERNMENTS - #18
SOUTH TEXAS DEVELOPMENT OF COUNCIL - #19
COASTAL BEND COUNCIL OF GOVERNMENTS - #20 | FY 20 - Q1 - 09/01/2020-11/31/2020
LOWER RIO GRANDE VALLEY DEVELOPMENT COUNCIL - #21 | FY 20 - Q2 - 12/01/2020-02/28/2021
TEXOMA COUNCIL OF GOVERNMENTS - #22 | FY 20 - Q3 - 03/01/2021-05/31/2021
CENTRAL TEXAS COUNCIL OF GOVERNMENTS - #23 | FY 20 - Q4 - 06/01/2021-08/31/2021
MIDDLE RIO GRANDE DEVELOPMENT COUNCIL - #24
FY 21 - Q1 - 09/01/2021-11/31/2021
SELECT THE REPORTING PERIOD FROM THE DROP DOWN MENU BY CLICKING IN THIS BOX | FY 21 - Q2 - 12/01/2021-02/28/2022
FY 21 - Q3 - 03/01/2022-05/31/2022
FY 21 - Q4 - 06/01/2022-08/31/2022
FY 20/21
Report #1 - September 1, 2019 - February 28, 2020 - Due March 30, 2020 | FY 22 - Q1 - 09/01/2022-11/31/2022
Report #2 - March 1, 2020 - August 31, 2020 - Due September 30, 2020 | FY 22 - Q2 - 12/01/2022-02/28/2023
Report #3 - September 1, 2020 - February 28, 2021 - Due March 30, 2021 | FY 22 - Q3 - 03/01/2023-05/31/2023
Report #4 - FINAL - March 1, 2021 - August 31, 2021 - Due December 31, 2021 | FY 22 - Q4 - 06/01/2023-08/31/2023
FY 22/23 | FY 23 - Q1 - 09/01/2023-11/31/2023
Report #1 - September 1, 2021 - February 28, 2022 - Due March 30, 2022 | FY 23 - Q2 - 12/01/2023-02/28/2024
Report #2 - March 1,2022 - August 31, 2022 - Due September 30, 2022 | FY 23 - Q3 - 03/01/2024-05/31/2024
Report #3 - September 1, 2022 - February 28, 2023 - Due March 30, 2023 | FY 23 - Q4 - 06/01/2024-08/31/2024
Report #4 - FINAL - March 1, 2023 - August 31, 2023 - December 31, 2023
Local Enforcement
Litter & Illegal Dumping/Community Cleanups
Source Reduction & Recycling
Local Solid Waste Management Plans
Citizens' Collection Station/Small Registered Transfer Station
HHW Management
Technical Studies
Education & Training
Other (Specify)
Attachments:
Equipment Inventory Log (Required)
COG-Managed Project Summary Form (CMP Form)
Other:
N/A
Select Yes, No or N/A From the Drop Down Menu By Clicking In This Box
Yes
No
N/A

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only