## Cover Page
Quarterly Progress Report
FY 2020 Q2
Entity: Houston-Galveston Area Council
Contract No: 582-20-10159
Project Name: Spring Creek Watershed Protection Plan Development
Date Submitted: 6/18/20
Contractor Project Manager: Justin Bower
Approval Signature: Date: 7/27/20
TCEQ Project Manager: Jessica Uramkin
Approval* Signature: Date:
* The TCEQ Project Manager's signature indicates that the QPR is accepted as a project deliverable and also authorizes any changes in deliverable due dates requested in the Deliverables sheet. Approved due date changes should be inserted in the "Current Due Date" column in the next QPR.
1. When ready to submit the QPR to TCEQ, the Contractor Project Manager must date and sign the cover page with an electronic signature (i.e., scanned signature). Send the signed Excel document to the TCEQ Project Manager.
2. The TCEQ Project Manager will review and either: 1) Send back with comments or 2) approve, sign, date, and e-mail a scanned copy of the approved QPR to the Contractor Project Manager.
3. After addressing comments email the updated Excel document the TCEQ Project Manager, along with a new date next to the electronic signature.
4. The TCEQ Project Manager will sign, date, scan and send the approved QPR to the Contractor Project Manager. A final version of the Excel document will also be sent.

## Deliverables
If a deliverable is or will be late, a new due date must be proposed. If this is the case, a justification describing the circumstances necessitating the new due date must be provided.
ID# | Sub Task # | Deliverable | Current Due Date | Date Sent | Discussion of Progress Last Quarter (Delete info from prior QPRs, and leave blank if no progress occurred) | Proposed New Due Date
12172 | 1.2 | QPR (20Q1) | 2019-12-15 | 2019-12-12 | Submitted to the TCEQ PM
12173 | 1.2 | QPR (20Q2) | 2020-03-15 | 2020-04-30 | Submitted to the TCEQ PM
12174 | 1.2 | QPR (20Q3) | 2020-06-15 | 2020-06-18 | Submitted to the TCEQ PM
12175 | 1.2 | QPR (20Q4) | 2020-09-15
12176 | 1.2 | QPR (21Q1) | 2020-12-15
12177 | 1.2 | QPR (21Q2) | 2021-03-15
12178 | 1.2 | QPR (21Q3) | 2021-06-15
12179 | 1.2 | QPR (21Q4) | 2021-09-15
12180 | 1.3 | Invoice (20Q1) | 12/131/2019 | 2020-01-27 | FSR to be submitted prior to the end of the month, after close of books for the quarter.
12181 | 1.3 | Invoice (20Q2) | 2020-03-30 | 2020-04-07 | Submitted to the TCEQ PM
12182 | 1.3 | Invoice (20Q3) | 2020-06-30
12183 | 1.3 | Invoice (20Q4) | 2020-09-30
12184 | 1.3 | Invoice (21Q1) | 2020-12-31
12185 | 1.3 | Invoice (21Q2) | 2021-03-31
12186 | 1.3 | Invoice (21Q3) | 2021-06-30
12187 | 1.3 | Invoice (21Q4)_June | 2021-07-15
12188 | 1.3 | Invoice (21Q4)_July | 2021-08-15
12189 | 1.3 | Invoice (21Q4)_Aug | 2021-10-15
12190 | 1.4 | Post-Award Notes | 2019-10-02 | 2019-09-30 | Post-award meeting held in Austin on 9/30/19.
12191 | 1.4 | Quarterly Call (20Q2) | 2020-02-29 | 2020-02-19 | Discussed progress, deliverable dates
12192 | 1.4 | Quarterly Call (20Q3) | 2020-05-31 | 2020-05-07 | Discussed progress, deliverable dates
12193 | 1.4 | Quarterly Call (20Q4) | 2020-08-31
12194 | 1.4 | Quarterly Call (21Q1) | 2020-11-30
12195 | 1.4 | Quarterly Call (21Q2) | 2021-02-28
12196 | 1.4 | Quarterly Call (21Q3) | 2021-05-31
12197 | 1.4 | Quarterly Call (21Q4) | 2021-08-31
12198 | 1.5 | EPA Coordination Call (If Requested) | 2022-08-31
12199 | 1.6 | Annual Report Article (If Requested) | 2022-08-31
12200 | 1.7 | FY21 Annual Budget Update | 2020-10-01
12201 | 1.7 | FY22 Annual Budget Update | 2021-10-01
12202 | 2.1 | QAPP Planning Meeting Notes | 2019-10-02 | 2019-09-30 | QAPP planning meeting held in Austin on 9/30/19.
12203 | 2.2 | Draft Modeling QAPP | 2019-12-31 | 2019-12-03 | QAPP submitted to TCEQ PM.
12204 | 2.2 | Final Modeling QAPP | 2020-02-29 | 2020-04-16 | QAPP executed 4/16/20
12205 | 3.1 | Ambient water quality analyses for Spring Creek | 2020-04-30 | 2020-05-26 | Data analyses for ambient data completed 4/30/20, report submitted to TCEQ PM on 5/26/20 | 2020-07-31
12206 | 3.1 | Ambient water quality analyses for Spring Creek (update in data analysis summary report) | 2021-06-30
12207 | 3.1 | Ambient water quality analyses for West Fork San Jacinto, Lake Creek, and Cypress Creek watersheds (in data analysis summary report update) | 2021-06-30
12208 | 3.2 | DMR and SSO analysis for Spring Creek | 2020-03-31 | 2020-05-26 | Data analyses for DMR and SSO data completed 4/30/20, report submitted to TCEQ PM on 5/26/20 | 2020-07-31
12209 | 3.2 | DMR and SSO analysis for Spring Creek (update, in data analysis summary report update) | 2021-06-30
12210 | 3.2 | DMR and SSO analysis for West Fork San Jacinto, Lake Creek, and Cypress Creek watersheds (in data analysis summary report update) | 2021-06-30
12211 | 3.3 | Data Analysis Summary Report for Spring Creek | 2020-07-31 | 2020-05-26 | Draft report submitted to TCEQ PM
12212 | 3.3 | Data Analysis Summary Report for Spring Creek (update) | 2021-06-30
12213 | 3.3 | Data Analysis Summary Report for West Fork San Jacinto, Lake Creek, and Cypress Creek watersheds | 2021-06-30
12214 | 4.1 | Update existing LDCs | 2020-06-30 | 2020-05-30 | LDC analysis of E. coli and DO at watershed sites referenced in QAPP complete | 2020-08-31
12215 | 4.2 | Update existing SELECT | 2020-07-31 |  |  | 2020-08-31
12216 | 4.3 | Draft Modeling Report | 2020-08-31
12217 | 4.3 | Final Modeling Report (30 days after TCEQ comments) | 2020-10-31
12218 | 5.1 | Draft PPP | 2020-01-15 | 2020-02-26 | Submitted to the TCEQ PM
12219 | 5.1 | Final PPP (30 days after TCEQ comments) | 2020-02-29 | 2020-02-26 | Submitted to the TCEQ PM
12220 | 5.2 | Stakeholder contact list | 2020-03-31 | 2020-06-18 | Submitted to the TCEQ PM
12221 | 5.2 | Stakeholder contact list | 2021-02-28
12222 | 5.3 | Stakeholder Communication Documentation (20Q1) | 2019-12-15 | 2019-12-12 | Attached as separate documentation with QPR for Q1.
12223 | 5.3 | Stakeholder Communication Documentation (20Q2) | 2020-03-15 | 2020-04-30 | Attached as separate documentation with QPR for Q2.
12224 | 5.3 | Stakeholder Communication Documentation (20Q3) | 2020-06-15 | 2020-06-18 | Attached as separate documentation with QPR for Q3.
12225 | 5.3 | Stakeholder Communication Documentation (20Q4) | 2020-09-15
12226 | 5.3 | Stakeholder Communication Documentation (21Q1) | 2020-12-15
12227 | 5.3 | Stakeholder Communication Documentation (21Q2) | 2021-03-15
12228 | 5.3 | Stakeholder Communication Documentation (21Q3) | 2021-06-15
12229 | 5.3 | Stakeholder Communication Documentation (21Q4) | 2021-09-15
12230 | 5.4 | Stakeholder Meeting Documentation (20Q2) | 2020-03-15 | 2020-04-30 | Attached as separate documentation with QPR for Q2.
12231 | 5.4 | Stakeholder Meeting Documentation (20Q3) | 2020-06-15 | 2020-06-18 | Attached as separate documentation with QPR for Q3.
12232 | 5.4 | Stakeholder Meeting Documentation (20Q4) | 2020-09-15
12233 | 5.4 | Stakeholder Meeting Documentation (21Q1) | 2020-12-15
12234 | 5.4 | Stakeholder Meeting Documentation (21Q2) | 2021-03-15
12235 | 5.4 | Stakeholder Meeting Documentation (21Q3) | 2021-06-15
12236 | 5.4 | Stakeholder Meeting Documentation (21Q4) | 2021-09-15
12237 | 5.5 | Other Public Meetings (1) | 2020-06-15 | 2020-06-18 | included with Task 5.3 Stakeholder Communication
12238 | 5.5 | Other Public Meetings (2) | 2020-09-15
12239 | 5.5 | Other Public Meetings (3) | 2020-12-15
12240 | 5.5 | Other Public Meetings (4) | 2021-03-15
12241 | 5.5 | Other Public Meetings (5) | 2021-06-15
12242 | 5.5 | Other Public Meetings (6) | 2021-09-15
12243 | 5.5 | Other Public Meetings (7+ as applicable) | 2021-09-15
12244 | 5.6 | Education and Outreach Event (1) | 2020-12-15
12245 | 5.6 | Education and Outreach Event (2) | 2021-03-15
12246 | 5.6 | Education and Outreach Event (3) | 2021-06-15
12247 | 5.6 | Education and Outreach Event (4) | 2021-09-15
12248 | 5.6 | Education and Outreach Event (5+ as applicable) | 2021-09-15
12249 | 5.7 | Draft watershed stakeholder coordination task report | 2021-06-30
12250 | 5.7 | Final watershed stakeholder coordination task report | 2021-08-31
12251 | 6.1 | WPP Development Update (20Q1) | 2019-12-15 | 2019-12-12 | H-GAC staff began updating information resources and non-QAPP coverage data from characterization report (stakeholder lists, conversations about watershed efforts, etc.)
12252 | 6.1 | WPP Development Update (20Q2) | 2020-03-15 | 2020-04-30 | H-GAC staff produced WPP Timeline and Document Review Plan, and Public Participation Plan
12253 | 6.1 | WPP Development Update (20Q3) | 2020-06-15 | 2020-06-18 | Aside from stakeholder development, no action taken
12254 | 6.1 | WPP Development Update (20Q4) | 2020-09-15
12255 | 6.1 | WPP Development Update (21Q1) | 2020-12-15
12256 | 6.1 | WPP Development Update (21Q2) | 2021-03-15
12257 | 6.1 | WPP Development Update (21Q3) | 2021-06-15
12258 | 6.1 | WPP Development Update (21Q4) | 2021-09-15
12259 | 6.2 | WPP timeline and document review plan | 2020-02-15 | 2020-02-17 | Submitted to the TCEQ PM
12260 | 6.2 | Draft nine-element WPP to stakeholders and the TCEQ | 2021-04-01
12261 | 6.2 | Revised nine-element WPP to EPA (30 days after stakeholder approval and TCEQ comments) | 2021-05-31
12262 | 6.2 | Draft Executive Summary | 2021-07-01
12263 | 6.2 | Final Executive Summary | 2021-08-01
12264 | 6.3 | Documentation of Executive Summary and Final WPP made available to stakeholders | 2021-08-31
12265 | 6.3 | Four hard copies and one electronic copy of final WPP Submitted to TCEQ | 2021-08-31
12266 | 7.1 | Final approved QPR as Final Report | 2021-09-15

## Narrative
Task/Issue | Additional Description of Quarterly Activities, Milestones, and Issues
1-Project Administration | QPR for Q2 submitted 4/30/20, delayed by COVID-19 response. Conference call held 5/7/20, notes approved on 5/8/20.
2-Quality Assurance | QAPP final draft approved, executed on 4/16/20.
3-Water Quality Data Acquisition and Evaluation | After QAPP approval, H-GAC staff analyzed ambient, DMR and SSO data for the Data Summary Report. The first draft of the report was subbmitted to TCEQ on 5/26/20.
4-Modeling | After QAPP approval, H-GAC staff used LDC modeling for E. coli and DO in the watershed. SELECT analysis to follow.
5-Watershed Stakeholder Coordination | In anticipation of the first public meeting (7/29), stakeholder relationship development has become the focus of recent interactions. Key partners (city, county, agency, and community organization representatives) have been contacted in one-on-one settings to explain project details and encourage participation in the steering committee. Several remote events have been attended in promotion of or as supplement to the project, see stakeholder contact documentation for more details.
6-WPP Development | No specific action was taken in this quarter. However, as described above, stakeholder coordination in anticipation of the first public meeting to beging the WPP process has been the focus of this quarter.
7-Final Report | No specific action was taken in this quarter.
Note: The purpose of this sheet is to provide for an ongoing discussion of tasks to document overall progress and to raise any overall issues that don't relate to specific deliverables.
Note: Please address activities and issues related to contract amendments, budget revisions, and other administrative matters under Task 1.

## Budget
Budget By Fiscal Year: Match and Federal totals
Section I: The current Budget by FY. If the last QPR had a new budget in Section III, that budget should be entered here.
Section II: The quarterly invoice totals to date this FY, and the estimated amounts for the quarter this QPR is reporting. If this table indicates the total spending this FY will be different from what is indicated in Section I, then enter a revised budget by FY in Section III.
Section III: A revised Budget by FY with justifications, entered whenever actual or expected spending is different from the current budget.
Section I: Current Budget by FY |  |  |  | Section II: Current FY Quarterly Spending:
| Match | Federal |  |  | Match | Federal
FY20: | 46650 | 69975 |  | Q1: | 3820.88 | 0
FY21: | 57017 | 85525 |  | Q2: | 12864.78 | 25733.74
|  |  |  | Q3: | 25478.22 | 38217.33
|  |  |  | Q4: |  | 38000 | estimate
Total: | 103667 | 155500 |  | Total: | 42163.88 | 101951.07
Section III: Has the total budget for this fiscal year changed? |  |  |  |  | Yes
If so, provide new budget by fiscal year estimates and justification for the change in the table below.
New Budget by FY:
| Match | Federal | Justification
FY20:
FY21:
Totals:

## QA_CA
Have any nonconformances occurred in the previous quarter? Yes/No |  |  |  | NA
Add any nonconformances and the corresponding corrective actions to the Corrective Action Status Table below. Nonconformances must be communicated to the NPS Project Manager immediately via email and a Corrective Action Plan submitted within 14 days of the nonconformance occurring.
Corrective Action Status Table
Corrective Action # | Date Issued | Description of Deficiency | Action Taken | Date Closed

## Attachments
Please provide a listing of deliverables provided along with the QPR, and delete attachment references from prior quarters. Reference the "Deliverables Report" to get the Deliverable ID, Subtask #, and Deliverable Name.
Deliverable ID | Subtask # | Deliverable Name | Attachment File Name
12224 | 5.3 | Stakeholder Communication Documentation (20Q3) | Stakeholder Communication FY20Q3.docx