## Cover Page
Quarterly Progress Report
FY20
Entity: H-GAC
Contract No: 582-20-10169
Project Name: Water Quality Management Planning
Date Submitted: 9/15/2020
Contractor Project Manager: Brian Sims
Approval Signature ____________________________ Date _09/15/20___
TCEQ Project Manager: Jessica Johnstone
Approval* Signature ____________________________Date __________
* The TCEQ Project Manager's signature indicates that the QPR is accepted as a project deliverable and also authorizes any changes in deliverable due dates requested in the Deliverables sheet. Approved due date changes should be inserted in the "Current Due Date" column in the next QPR.
1. When ready to submit the QPR to TCEQ, the Contractor Project Manager must date and sign the cover page with an electronic signature (i.e., scanned signature). Send the signed Excel document to the TCEQ Project Manager.
2. The TCEQ Project Manager will review and either: 1) Send back with comments or 2) approve, sign, date, and e-mail a scanned copy of the approved QPR to the Contractor Project Manager.
3. After addressing comments email the updated Excel document the TCEQ Project Manager, along with a new date next to the electronic signature.
4. The TCEQ Project Manager will sign, date, scan and send the approved QPR to the Contractor Project Manager. A final version of the Excel document will also be sent.

## Deliverables
If a deliverable is or will be late, a new due date must be proposed. If this is the case, a justification describing the circumstances necessitating the new due date must be provided.
ID# | Sub Task # | Deliverable | Current Due Date | Date Sent | Discussion of Progress Last Quarter (Delete info from prior QPRs, and leave blank if no progress occurred) | Proposed New Due Date
11249 | 1.2 | QPR (FY20Q1) | 2019-12-15 | 2019-12-13 | QPR submitted via email by Brian Sims
11250 | 1.2 | QPR (FY20Q2) | 2020-03-15 | 2020-03-14 | QPR submitted via email by Brian Sims
11251 | 1.2 | QPR (FY20Q3) | 2020-06-15 | 2020-06-11 | QPR submitted via email by Brian Sims
11252 | 1.2 | QPR (FY20Q4) | 2020-09-15 | 2020-09-15 | QPR submitted via email by Brian Sims
11253 | 1.3 | Invoice (FY20Q1) | 2019-12-30 | 2019-12-30 | QPR submitted
11254 | 1.3 | Invoice (FY20Q2) | 2020-03-30 | 2020-03-19 | QPR submitted by Treebie Vasquez
11255 | 1.3 | Invoice (FY20Q3) | 2020-06-30 | 2020-06-30 | QPR submitted by Treebie Vasquez
11256 | 1.3 | Invoice (FY20Q4)_June | 2020-07-15 | 2020-07-15 | QPR submitted by Treebie Vasquez
11257 | 1.3 | Invoice (FY20Q4)_July | 2020-08-15 | 2020-08-17 | QPR submitted by Treebie Vasquez
11258 | 1.3 | Invoice (FY20Q4)_August | 2020-10-15 | 2020-09-15 | Invoice submitted electronically by Treebie Vasquez
11259 | 1.4 | Post-Award Mtg | 2019-10-01 | 2019-09-30 | The Post-Award Meeting was held in Austin on 9/30/19.
11260 | 1.4 | Post-Award Notes | 2019-10-03 | 2019-12-13 | Notes included as attachment with QPR. I belive they were submitted previously, but cannot located documentation of such.
11261 | 1.4 | Quarterly Call and Notes (FY20Q2) | 2020-03-31 | 2020-03-26 | Conference call notes submitted by email. Copy included as attachment. | Due date changed to reflect contract terms- due "within 30 days of the end of each quarter".
11262 | 1.4 | Quarterly Call and Notes (FY20Q3) | 2020-06-30 | 2020-07-07 | Conference call notes submitted by email. | Due date changed to reflect contract terms- due "within 30 days of the end of each quarter".
11263 | 1.4 | Quarterly Call and Notes (FY20Q4) | 2020-09-30 | Pending | Q4 conference call pending execution of FY 21 contract. | Due date changed to reflect contract terms- due "within 30 days of the end of each quarter".
11264 | 1.4 | Notification of scheduled public meetings or events (14 days prior to meeting or event) | 2020-08-31 | 2020-08-31 | Occurs throuhgout project cycle
11265 | 1.4 | Information regarding events or circumstances that may require changes to the Budget, Scope of Work, or Schedule of Deliverables (within two working days of discovery) | 2020-08-31 | 2020-08-11 | Budget Revision Request No. 1 submitted on 8/11/20 and approved on 8/12/20
11266 | 2.1 | QAPP Planning Meeting and Notes | 2019-10-01 | 2019-12-13 | Included with Post-Award meeting notes. QAPP revision already underway at time of meeting.
11267 | 3.1 | Wastewater Infrastructure Geographic Information System (GIS) Data update to include maps with service area boundaries, wastewater outfalls, and SSO analyses | 2020-07-01 | 3/14/20 7/1/2020 | Received updated GIS layer for WWTF permits from TCEQ. Submitted electronically with Draft WQMP Update Report
11268 | 3.2 | Summary Report of Regional SSO and DMR Data Analyses | 2020-07-01 | 2020-07-01 | Included in Draft WQMP Update Report
11269 | 3 | Summary of Task Activities (in QPRs) | 2020-08-31 | 2020-08-31 | Included in QPRs throughout project
11270 | 4.1 | San Bernard River meeting materials and summary (at least one; within 30 days of meeting) | 2020-08-31 | 2020-08-31 | No in-person meeting held this year due to COVID-19. Numerous telephone dicussions, documented in QPRs throughout project.
11271 | 4.2 | FY20Q1 NRAC meeting materials and summary | 2019-11-30 | 2019-12-13 | The FY20Q1 NRAC meeting was held on 11/7/19. The agenda and draft meeting minutes are attached to the QPR. Minute meetings are not final until approved at the next quarterly NRAC meeting.
11272 | 4.2 | FY20Q2 NRAC meeting materials and summary | 2020-02-29 | 2020-02-17 | NRAC meeting held on 2/6/20. Meeting materials submitted by email on 2/17/20
11273 | 4.2 | FY20Q3 NRAC meeting materials and summary | 2020-03-31 | 2020-05-06 | NRAC meeting held on 5/7/20. Meeting materials attached.
11274 | 4.2 | FY20Q4 NRAC meeting materials and summary | 2020-08-31 | 2020-09-15 | Meeting held 8/6/20. Materials included with QPR.
11275 | 4.3 | Meeting materials and summary for at least one workshop for urban forestry practicioners (within 30 days of meeting) | 2020-08-31 | 2020-08-31 | Included in QPRs throughout project
11276 | 4.4 | Meeting materials and summary for up to eight TMDL project meetings (within 30 days of meeting) | 2020-08-31 | 3/14/20 6/11/20 | Meeting materials for San Jacinto - Brazos Coastal Basin Public Outreach Meeting attached. Meeting held 1/30/2020. Meeting materials for TMDL attached.
11277 | 4 | Summary of Task Activities (in QPRs) | 2020-08-31 | 2020-08-31 | Included in QPRs throughout project
11278 | 5.1 | Updated permitted OSSF database | 2020-07-01 | 2020-07-01 | Submitted electronically with Draft WQMP Update Report
11279 | 5.2 | Updated unpermitted OSSF location and analysis | 2020-07-01 | 2020-07-01 | Included in Draft WQMP Update Report
11280 | 5.3 | List of training provided for AAs; documentation of submitted OSSF updates by AAs (in QPRs) | 2020-08-31 | 2019-12-13 | Included in QPR narrative section
11281 | 5.3 | Materials and summaries from meetings and/or trainings with AAs (within 30 days of event) | 2020-08-31 | 12/13/19 9/15/20 | Presentation from Harris County Onsite Wastewater Seminar included with attachments.
11282 | 5.4 | List of activities (meetings, inspections, travel, etc.) related to OSSF SEP program (in QPRs) | 2020-08-31 | 12/13/2019 3/14/2020 6/11/2020 9/15/2020 | Included in QPR narrative section
11283 | 5.5 | List of OSSF trainings provided for homeowners, and number of attendees (in QPRs) | 2020-08-31 | 2019-12-13
11284 | 5.5 | Meeting materials and summaries from educational training courses for homeowners (within 30 days of event) | 2020-08-31 | 2019-12-13
11285 | 5 | Summary of Task Activities (in QPRs) | 2020-08-31 | 12/13/2019 3/14/2020 6/11/2020 9/15/2020 | Included in QPR narrative section
11286 | 6.1 | Draft 2020 WQMP Update | 2020-07-30 | 2020-07-01 | Draft 2020 WQMP Update posted to H-GAC website, distributed to NRAC, and submitted to TCEQ Project Manager
11287 | 6.1 | Documentation of Public Participation for WQPM Update | 2020-08-15 | 2020-07-07 | Email to TCEQ PM documenting start of public comment period
11288 | 6.2 | Final 2020 WQMP Update in hardcopy and electronic format, and H-GAC Board approval (when available) | 2020-08-28 | 2020-08-28 | Final WQMP report emailed to TCEQ PM on 8/20/20. Hard copies to be mailed by 08/28/20.
11289 | 7.1 | Draft Final Report | 2020-07-20 | 2020-07-20 | Draft Final Summary Report submitted to TCEQ PM by email
11290 | 7.2 | Final Report | 2020-08-20 | 2020-08-20 | Final Summary Report submitted to TCEQ PM by email

## Narrative
Task/Issue | Additional Description of Quarterly Activities, Milestones, and Issues
1-Project Administration | Quarter 1 Brian Sims prepared and submitted the Quarterly Progress Report. Information was not available from Finance at the time of the QPR due date to complete the Budget tab. This information will be provided when available. Quarter 2 Brian Sims performed project oversight and maintained contract communication with TCEQ. Brian Sims prepared and submitted the Quarterly Progress Report. Todd Running responded to the FY2021 604(b) Interest Inquiry. Brian Sims prepared a Draft Scope of Work and Draft Budget for the FY21 project (see attachments). Quarter 3 Brian Sims performed project oversight and maintained contract communication with TCEQ. Brian Sims prepared and submitted the Quarterly Progress Report. A quarterly conference call was held on 3/26/20. A copy of the conference call nots is included in the attachments. Brian Sims submitted the FY2021 Budget by Task on 4/29/20. A copy of the budget is attached. Quarter 4 Brian Sims performed project oversight and maintained contract communication with TCEQ. Brian Sims prepared and submitted the Quarterly Progress Report. A budget revision was submitted in Q4. Brian Sims prepared the contractor self-evaluation.
2-Quality Assurance | Quarter 1 Brian Sims prepared the project QAPP. This QAPP combined the two previous QAPPs (Geospatial and Data Acquisition) into one document. The Combined QAPP was submitted 10/1/19. Brian Sims responsed to comments and resubmitted draft 2 on 11/12/19. Jessica Johnstone incorporated the minor changes requested for the draft into a final document and routed it for approval. Brian Sims submitted H-GAC's signature pages on 12/9/19. Quarter 2 Brian Sims submitted H-GAC's QAPP signature pages on 12/9/19. The H-GAC Data Acquisition and Geospatial Data QAPP was distributed to staff on 12/31/19. See attachments. Quarter 3 No activity this quarter. Quarter 4 Brian Sims reviewed the Data Acquisition and Geospatial QAPP. Brian Sims prepared and submitted Expedited Amendment #1 to the QAPP.
3-WWTF Data Update & Coordination/GIS) | Quarter 1 H-GAC continued efforts to acquire Sanitary Sewer Overflow data from TCEQ Region 12. Quarter 2 Task 3.2 Wastewater Data Analysis H-GAC continued efforts to acquire Sanitary Sewer Overflow data from TCEQ Region 12. Brian Sims contacted Katie Cunningham with TCEQ Central Office on 2/20/20 to receive the most current Municipal/Industrial WWTF Outfall data layer. Brian Sims, Jessica Casillas, and Thushara Ranatunga met on 2/26 to discuss the data layer, and submitted a list of data discrepancies discovered to Katie Cunningham (see attachments). Task 3.3 CWSRF Application Review Brian Sims reviewed and prepared a response to the CWSRF application for Harris Co. MUD #148. See attachments. Quarter 3 Task 4.2 Coordination The NRAC meeting was held on 5/7/20. Meeting minutes are included as an attachment. Brian Sims presented on the status of the Water Quality Management Plan. A copy of the presentation is included as an attachment. Task 4.3 Urban Forestry Support and Coordination Justin Bowers worked primarily wih supporting Urban Forestry Activities. These included: Had two journal articles published (in partnership with the City of Houston and the NYC Natural Areas Conservancy) in the journal Cities and the Environment; Represented or coordinated forestry interests for inclusion in several water quality planning and conservation planning projects (Cypress Creek WPP, Spring Creek WPP, Big Creek TMDL, et al.); Worked with local partners (USDA NRCS, USFS, Texas A&M FS) on identifying potential reforestation and riparian buffer projects in priority watersheds; Worked with the City of Houston to identify funding sources and project scoping for a conservation master plan targeting forested natural areas in public lands; Served on the Coordinating Committee for the statewide Forests and Drinking Water Partnership; Served on the USDA NRCS State Technical Advisory Committee group for urban areas, representing forestry; Represented H-GAC and partner water quality efforts in discussions with various foresty stakeholders throughout the period, including Texas A&M Forest Service, Texas A&M AgriLife, City of Houston Source Water Protection, et al; Served on the Board of the Houston Area Urban Forestry Council to represent watershed projects and water quality efforts in the area. Task 4.4 Public Support for TMDL Projects Steven Johnson coordinated TMDL project activities. • H-GAC hosted the Caney Creek Watershed Coordination Committee meeting in support of the Basin 13 TMDL and implementation plan development on March 17th. Staff support included time for meeting preparations and communication with stakeholders in advance of the meeting. The meeting was held as a webinar due to COVID-19. A meeting summary and other materials has been attached. • H-GAC hosted the BIG Coordination and Policy work group on March 23, 2020. Staff support included time for meeting preparations and communication with stakeholders in advance of the meeting. This meeting was held as a conference call due to COVID-19. A meeting summary and other materials has been attached. • H-GAC hosted the BIG Coordination and Policy work group on May 28, 2020. Staff support included time for meeting preparations and communication with stakeholders in advance of the meeting. The meeting was held as a webinar due to COVID-19. A meeting summary and other materials has been attached. Additionally, support for the BIG Spring meeting development was carried out during the quarter (Agenda attached). Quarter 4 Results of this task reported in the WQMP Update report.
4-Support Watershed Planning | Quarter 1 Task 4.3 Urban Forestry Support and Coordination Justin Bower worked primarily wih supporting Urban Forestry Activities. These included: Worked with the City of Houston and other partners on grant proposals to increase planning and implementation projects for forested natural areas.; Attended and presented at an urban forestry conference in NYC to a selection of other cities across the country; Met with Texas Forest Service staff to plan coordination opportunities for urban forestry projects in the Houston area; Had a presentation on water quality and urban forestry accepted for the GBEP symposium; Attended the Houston Urban Tree conference and presented on water quality and forestry practices; Coordinated 604b forestry efforts with WPP efforts in Cypress Creek, Spring Creek, and the upcoming Regional Conservation Framework project. Relevant meeting materials are included in the attachments. Task 4.4 Public Support for TMDL Projects Steven Johnston performed work in preparation for several presentations and meetings related to TMDL projects. However, while the preparation for these meetings primarily occurred during Q1, the meetings did not occur until Q2. Meeting materials and agendas will be included with the QPR for Q2. Quarter 2 Brian Sims attended the Region H Water Planning Group meeting on 1/8/20. A copy of the agenda is attached. Task 4.1 San Bernard River Watershed Coordination Justin Bower worked with local government partners to develop a coordinated resilience/water quality project similar to the Cedar Bayou Initiative, a coordinated project of several counties and municipalities that included water quality issues in flood mitigation discussions. H_GAC is continuing ti support a future project on the San Bernard River. Justin Bower also provided technical support (mapping) for a local NGO service provider (Friends of the River San Bernard) to help with outreach efforts in the watershed. Task 4.2 Coordination The NRAC meeting was held on 2/6/20. Meeting minutes are included as an attachment. Brian Sims attended the Region H Water Planning Group meeting. Task 4.3 Urban Forestry Support and Coordination Justin Bower worked primarily wih supporting Urban Forestry Activities. These included: Served in a leadership role on the Houston Area Urban Forestry Council; Served on the USDA NRCS’s Urban State Technical Advisory Committee, looking at forestry and working lands in urban areas; Supported several local governments/partners with forestry-related data and analysis (Houston parks, Houston source water protection, Texas A&M Forest Service, Nature Conservancy, et al.); Supported local government and partner projects (Texas A&M Forest Service natural resources leadership planning, planning for upcoming Texas Forests and Drinking Water Partnership efforts, etc); Facilitated inclusion of forestry partners and practices in water quality planning efforts (WPPs, etc.); Drafted an urban forestry journal article in conjunction with the City of Houston that was accepted by the Journal of Cities and the Environment (CATE) Task 4.4 Public Support for TMDL Projects H-GAC hosted the Chocolate Bay Watershed Public Meeting in support of the Basin 11 TMDL work in Chocolate, Halls and Mustang Bayous. Staff support included time preparing for the meeting, emailing meeting announcements, travel to attend the meeting and meeting facilitation. A meeting summary and other materials has been attached. Quarter 3 Task 4.2 Coordination The NRAC meeting was held on 5/7/20. Meeting minutes are included as an attachment. Brian Sims presented on the status of the Water Quality Management Plan. A copy of the presentation is included as an attachment. Task 4.3 Urban Forestry Support and Coordination Justin Bower worked primarily wih supporting Urban Forestry Activities. These included: Had two journal articles published (in partnership with the City of Houston and the NYC Natural Areas Conservancy) in the journal Cities and the Environment; Represented or coordinated forestry interests for inclusion in several water quality planning and conservation planning projects (Cypress Creek WPP, Spring Creek WPP, Big Creek TMDL, et al.); Worked with local partners (USDA NRCS, USFS, Texas A&M FS) on identifying potential reforestation and riparian buffer projects in priority watersheds; Worked with the City of Houston to identify funding sources and project scoping for a conservation master plan targeting forested natural areas in public lands; Served on the Coordinating Committee for the statewide Forests and Drinking Water Partnership; Served on the USDA NRCS State Technical Advisory Committee group for urban areas, representing forestry; Represented H-GAC and partner water quality efforts in discussions with various foresty stakeholders throughout the period, including Texas A&M Forest Service, Texas A&M AgriLife, City of Houston Source Water Protection, et al; Served on the Board of the Houston Area Urban Forestry Council to represent watershed projects and water quality efforts in the area. Task 4.4 Public Support for TMDL Projects Steven Johnson coordinated TMDL project activities. • H-GAC hosted the Caney Creek Watershed Coordination Committee meeting in support of the Basin 13 TMDL and implementation plan development on March 17th. Staff support included time for meeting preparations and communication with stakeholders in advance of the meeting. The meeting was held as a webinar due to COVID-19. A meeting summary and other materials has been attached. • H-GAC hosted the BIG Coordination and Policy work group on March 23, 2020. Staff support included time for meeting preparations and communication with stakeholders in advance of the meeting. This meeting was held as a conference call due to COVID-19. A meeting summary and other materials has been attached. • H-GAC hosted the BIG Coordination and Policy work group on May 28, 2020. Staff support included time for meeting preparations and communication with stakeholders in advance of the meeting. The meeting was held as a webinar due to COVID-19. A meeting summary and other materials has been attached. Additionally, support for the BIG Spring meeting development was carried out during the quarter (Agenda attached). Quarter 4 Task 4.2 Coordination The NRAC meeting was held on 8/6/20. Meeting agenda is included as an attachment. Brian Sims presented on the Water Quality Management Plan. A copy of the presentation is included as an attachment. Task 4.3 Urban Forestry Support and Coordination Attended the Texas Forests & Drinking Water Partnership meeting. Minutes attached.
5-OSSF Program Support | Quarter 1 Task 5.4 SEP Administration and Coordination 10/15/19 - Presenation at the Texas Environmental Health Association Annual Education Conference in Austin (42 participants) On 11/12/19, Brian Sims participated in a webinar on SEPs sponsored by TCEQ and NCTCOG. Task 5.5 OSSF Outreach and Education Discussions began with North Central Texas Council of Governments (NCTCOG) to hold a OSSF Visual Inspection Course for Real Estate Inspectors in March or April 2020. The following OSSF meetings/education courses were conducted: 10/5/19 - OSSF Homeowner's Education Course in Bailey's Prairie (11 participants) 10/12/19 - OSSF Homeowner's Education Course at Brazosport College (6 participants) Quarter 2 Task 5.1 Permitted OSSF Update Jessica Casillas continued data entry for permitted OSSF data received from Authorized Agents. Task 5.3 Outreach to Authorized Agents Brian Sims began contacting Authorized Agents, particularly those who had not submitted recent data. Several of these agents had stopped submitting data due to staff turnover at both H-GAC and the permitting agencies. Lines of communication are being reestablished. Internal discussions have initiated regarding scheduling a joint meeting of the Authorized Agents later in the year. Task 5.4 SEP Administration and Coordination H-GAC received $10,000 in funding from the Harris County District Attorney's Office to be used for repair or replacement of failed OSSFs throughout the region. Two candidates needing system repairs were identified and the procurement process was initiated. Task 5.5 OSSF Outreach and Education Brian Sims was in discussion with North Central Texas Council of Governments (NCTCOG) to present a Real Estate Inspector's OSSF Visual Inspection Course. The tentative date is in April. Quarter 3 Task 5.1 Permitted OSSF Update Jessica Casillas completed data entry for permitted OSSF data received from Authorized Agents through 12/31/19. Task 5.3 Outreach to Authorized Agents Brian Sims contacted Authorized Agents to assess response to COVID-19 and adjustments (if any) to the AA's permitting and enforcement activities. Task 5.4 SEP Administration and Coordination H-GAC received an additional $30,000 in funding this quarter from the Harris County District Attorney's Office to be used for repair or replacement of failed OSSFs throughout the region. These funds are not a part of the TCEQ Supplemental Environmental Project funds, but are used in a similar fashion. Coordination of repairs/replacements using these funds falls under Task 5.4. Task 5.5 OSSF Outreach and Education The Real Estate Inspector's Visisual Inspection Course for be conducted for the North Central Texas Council of Governments (NCTCOG) has been postponed due to COVID-19. A new date has not been set. Brian Sims was scheduled to present at Harris County's Annual On-Site Wastewater Program in May, but the meeting was postponed due to COVID-19. It will most likely be held by webinar sometime in August. Quarter 4 OSSF database update included in WQMP Update Report. Brian Sims presented at the Harris County Onsite Wastewater Seminar. A copy of the presentation is included.
6-WQMP Update | Quarter 1 No activity this quarter. Quarter 2 No activity this quarter Quarter 3 Brian Sims began preparation of the Draft WQMP Update, to be submitted by 7/1/20. Quarter 4 Brian Sims completed the WQMP Update Report and the WQMP Project Summary Report. The reports were posted to H-GAC's website. Hardcopy reports were mailed to TCEQ.
Note: The purpose of this sheet is to provide for an ongoing discussion of tasks to document overall progress and to raise any overall issues that don't relate to specific deliverables.
Note: Please address activities and issues related to contract amendments, budget revisions, and other administrative matters under Task 1.

## Budget
This tab is used for budget planning purposes. The TCEQ uses the information quarterly for program budget planning. It is important this form is completed to avoid rush requests from the TCEQ Project Manager. Section I tracks the current budget by fiscal year. This information is from the Annual Budget Update. This is a high-level overview of planned spending for each year of the project. Changes to fiscal year estimates are noted in Section III. After the current QPR is approved the new fiscal year estimates should be moved from Section III to Section I. Section II tracks the current fiscal year's invoicing. Include invoices that have been approved by TCEQ and estimates for upcoming invoices. Section III tracks changes in the fiscal year budgets. Changes may be an increase or a decrease in spending from original estimate. After the current QPR is approved the new fiscal year estimates should be moved from Section III to Section I.
Section I: Current Budget by FY |  |  |  | Section II: Current FY Quarterly Spending:
| Match | Federal |  |  | Match | Federal
FY20: | 0 | 136588 |  | Q1: | $0.00 | 23335.09
|  |  |  | Q2: | 0 | 41530.76
|  |  |  | Q3: | 0 | 48595.32
|  |  |  | Q4: | 0 | 23126.83
Total: | 0 | 136588 |  | Total: | 0 | 136588
Section III: Has the total budget for this fiscal year changed? |  |  |  |  | No
If so, provide new budget by fiscal year estimates and justification for the change in the table below.
New Budget by FY:
| Match | Federal | Justification
FY20:
Totals:

## QA_CA
Have any nonconformances occurred in the previous quarter? Yes/No
Add any nonconformances and the corresponding corrective actions to the Corrective Action Status Table below. Nonconformances must be communicated to the NPS Project Manager immediately via email and a Corrective Action Plan submitted within 14 days of the nonconformance occurring.
Corrective Action Status Table
Corrective Action # | Date Issued | Description of Deficiency | Action Taken | Date Closed

## Attachments
Please provide a listing of deliverables provided along with the QPR, and delete attachment references from prior quarters. Reference the "Deliverables Report" to get the Deliverable ID, Subtask #, and Deliverable Name.
Deliverable ID | Subtask # | Deliverable Name | Attachment File Name
| 1 | Contractor Self Evaluation | Contractor Self Evaluation
| 1 | Interest Inquiry | 1a - RE_ FY2021 604(b) Interest Inquiry.pdf
| 1 | FY21 Scope of Work | 1b - FY21 HGAC 604b SOW Draft 2 2020-02-10.pdf
| 1 | FY21 Budget | 1c - HGAC_FY21_604b_Budget - 2.12.2020.pdf
| 1 | FY 2021 Budget | 1.0 - Email - Budget by Task.pdf 1.0 - H-GAC_FY21_0604b_Budget by Task - 04.29.2020.pdf
11260 | 1.4 | Post-Award Notes | 11260 - FY20 Post Award Meeting Notes.pdf
11265 | 1.4 | Information regarding events or circumstances that may require changes to the Budget, Scope of Work, or Schedule of Deliverables (within two working days of discovery) | 11265 - 0169_BRR1_executed
11262 | 1.4 | Quarterly Call and Notes (FY20Q2) | 11262 - Conference Call Notes FY20 Q2 - 03-26-2020.pdf
| 2 | Annual QAPP review and certification | QAPP Annual Review Certification
| 2 | QAPP signature page | Task 2 HGAC 604b Combined QAPP Signature Page (1).pdf
| 2 | QAPP distribution | 2 FW_ New H-GAC Water Quality Management Plan Data Acquisition and Geospatial Data QAPP.pdf
11267 | 3.1 | Wastewater Infrastructure Geographic Information System (GIS) Data update to include maps with service area boundaries, wastewater outfalls, and SSO analyses | 3.2a RE_ Request for Municipal_Industrial WWTF Outfalls GIS layer1.pdf 3.2a RE_ Request for Municipal_Industrial WWTF Outfalls GIS layer.pdf
| 3.3 | CWSRF Review | 3.3 73832 Harris County MUD 148 2020-01-20.pdf 3.3 RE_ Harris County Municipal Utility District (MUD) No_ 148 Project No_ 7383220-01-20.pdf
11271 | 4.2 | FY20Q1 NRAC meeting materials and summary | 11271 - 2019-11-07_NRAC Agenda.pdf 11271 - 2019-11-07_NRAC Minutes.pdf
11274 | 4.2 | FY20Q4 NRAC meeting materials and summary | 11274 - 2020-08-06 NRAC WQMP Presentation
11274 | 4.2 | FY20Q4 NRAC meeting materials and summary | 11274 - 2020-08-06_NRAC Agenda
| 4.2 | Region H Water Planning Group | 4.2 Region H Water Planning Group - 2020-01-08.pdf
11272 | 4.2 | FY20Q2 NRAC meeting materials and summary | 4.2 11272 - NRAC Meeting Minutes 02-06-2020.pdf
11273 | 4.2 | FY20Q3 NRAC meeting materials and summary | 11273 - 2020-02-06_NRAC Minutes.pdf 11273 - 2020-05-07_NRAC Agenda.pdf 11273 - NRAC WQMP Update May 2020.pdf
11275 | 4.3 | Meeting materials and summary for at least one workshop for urban forestry practicioners (within 30 days of meeting) | 11275 - Texas Forests & Drinking Water Partners Zoom Call Notes 61020
| 4.3 | Forestry meeting materials | Task 4.3 Forests In Cities_Workshop packet 10.20.docx.pdf Task 4.3 Houston Urban Tree Conference.pdf
11275 | 4.3 | Meeting materials and summary for at least one workshop for urban forestry practicioners (within 30 days of meeting) | 4.3 - Assessing Houston_s Forested Habitat.pdf 4.3 - Planning for Climate Change Through Riparian Restoration.pdf 4.3 - Journal article email.pdf
11276 | 4.4 | Meeting materials and summary for up to eight TMDL project meetings (within 30 days of meeting) | 11276 - PublicMeeting5.pdf
11276 | 4.4 | Meeting materials and summary for up to eight TMDL project meetings (within 30 days of meeting) | 4.4 - BIGSpring_06022020_meetingpacket.pdf 4.4 - Public_Outreach_Report_CC5.pdf 4.4 - Summary03232020.pdf 4.4 - Summary05282020.pdf
11281 | 5.3 | Materials and summaries from meetings and/or trainings with AAs (within 30 days of event) | 11281 - HC Webinar Series Agenda Topics 2020
11281 | 5.3 | Materials and summaries from meetings and/or trainings with AAs (within 30 days of event) | 11281 - H-GAC NPS OSSF 2020-08-05 BS
11281 | 5.3 | Materials and summaries from meetings and/or trainings with AAs (within 30 days of event) | 11281 - 2019-10-15 OSSF SEP TEHA Presentation PDF 11281 - 20191007195540_6_2019programataglanceannouncement.pdf 11281 - TEHA Abstract Sims.pdf
11284 | 5.5 | Meeting materials and summaries from educational training courses for homeowners (within 30 days of event) | 11284 - Homeowners Education Course - Brazosport College - 2019-10-12.pdf
11287 | 6.1 | Documentation of Public Participation for WQPM Update | 11287 - WQMP Board Agenda Item