## Project Information (hidden)
LPA Project Design Schedule Tool
Sponsor
County
Roadway/ Structure ID
Project Limits
Project Length
AADT Traffic Count/ Count Year
Program Cycle (Start/ End Year)
Time Estimation | Criteria
Project Scope | Reconstruction
Project Location | Metropolitan
Design Funding (Estimated Cost) | Yes $200k to $1million
ROW Status | Less than 1/2 acre
Railroad Present | Within 100ft of Railroad ROW
Utility Timeline | Reconstruction
Environmental Complexity | #REF!
Minimum Project Timeline
Environment Complexity Checklist | Yes | No
Real Estate > 0.5 acres | TRUE | FALSE
Curb Ramps in Project Limits | FALSE | TRUE
Roadway/ Structure Widening | FALSE | FALSE
Project to Impact Public Land | TRUE | FALSE
Excavation Deeper than 2ft | TRUE | FALSE
Historical Property in Limits | FALSE | FALSE
Archeological Site in Limits | TRUE | FALSE
Project to Impact Floodplain | FALSE | FALSE
Hazardous Material Open Site | FALSE | TRUE
Endangered Species Mitigation | FALSE | FALSE
Wetland or Waterway Impacts | FALSE | FALSE
Public Concerns with Project | FALSE | FALSE
Other Project Concerns | TRUE | FALSE
Environmental Complexity | #REF!
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Railroad coordination process (not certification)

## Project Info
Local Government Preliminary Scheduling Tool
Basic Project Information
Project Name
Sponsor (Owner) | ZYX County
County | XYZ
CSJ
Roadway/ Structure ID
Project Limits
Project Length
Project Location | Metropolitan
LG Risk Score | D
AADT Traffic Count/ Count Year | 45,000 - 2024
Estimated Construction Cost | 10000000
Project Initiation Date | 2025-01-01

## LPA Schedule Tool- No Schematic
Local Government Preliminary Scheduling Tool- No Schematic
AFA Process | Criteria
Has the AFA been completed? | FALSE
Procure Consultant | Criteria
Has the consultant selection process been approved by TxDOT | Non-federal procurement process- Consultant Selected
Schematic/Preliminary Design | Criteria
Check if schematic phase is needed | FALSE
Design | Criteria
Project Scope | Widen Non-Freeway
Check if this a FHWA Major Project or is a Value Engineering Study is proposed | FALSE
ROW | Criteria
Type of Parcels Checklist
Easements | FALSE
Undeveloped Acreage | FALSE
Residential | FALSE
Commercial | FALSE
Industrial | FALSE
How many parcels will there be?
Check if pushback is anticipated | FALSE
Check if the ROW phase will be managed by TxDOT? | FALSE
Utilities | Criteria
Type of Utilities Checklist
Fiber Optic | FALSE
Gas | FALSE
Water | FALSE
Overhead Transmission | FALSE
Duct Bank | FALSE
How many total utilities provider's fracilities will be impacted by this project?
Check if the utilities phase be managed by TxDOT | FALSE
Railroad | Criteria
Railroad Present
Check if the railroad phase be managed by TxDOT | FALSE
Environmental Complexity Selection | Criteria
Environmental Documentation Needed
Check if the environmental clearance phase be managed by TxDOT? | FALSE

## Schedule Output- No schematic
Local Government Preliminary Scheduling Tool
No Schematic
Basic Project Information
Project Name | 0
Sponsor (Owner) | ZYX County
County | XYZ
CSJ | 0
Roadway/ Structure ID | 0
Project Limits | 0
Project Length | 0
Project Location | Metropolitan
LG Risk Score | D
AADT Traffic Count/ Count Year | 45,000 - 2024
Estimated Construction Cost | 10000000
Project Initiation Date | 2025-01-01
Local Government Preliminary Scheduling Tool
Ref # | OPC Activity ID | Recommended Schedule | Months | Forecast Start Date | Forecast Finish Date | Predecessors | Successors
1 | START | Start Milestone | 0 | 2025-01-01 |  |  | 2
2 | AFACOMP | AFA Complete | 8 | 2025-01-01 | 2025-09-01 | 1 | 3
3 | PROCON | Procure Consultant | 0 | 2025-09-01 | 2025-09-01 | 2 | 5,9
5 | A1000 | Start Design Date | 0 | 2025-09-01 |  | 3 | 6,9
6 | DES030 | PS&E 30% Complete Milestone | 7 | 2025-09-01 | 2026-04-01 | 5 | 7,10,11,12
7 | DES060 | PS&E 60% Complete Milestone | 7 | 2026-04-01 | 2026-11-01 | 6 | 8
8 | DES095 | PS&E 95% Complete Milestone | 7 | 2026-11-01 | 2027-06-01 | 7 | 13
9 | ENVCLR | Environmental Clearance for Letting Milestone | #N/A | 2026-11-01 | #N/A | 7 | 14
10 | RRCERT | Railroad Coordination Complete | #N/A | 2026-04-01 | #N/A | 6 | 14
11 | ROWCERT | ROW Possessed Milestone | 0 | 2026-04-01 | 2026-04-01 | 6 | 9FF*, 14
12 | UTLCERT | Utilities Adjusted Milestone | 0 | 2026-04-01 | 2026-04-01 | 6 SF | 14
13 | DES100 | PS&E 100% Complete Milestone | 2 | 2027-06-01 | 2027-08-01 | 8 | 14
14 | RTL1000 | Ready to Let Milestone |  | #N/A | #N/A | 9,10,11,12,13
|  | Total | #N/A
|  | AFA Coordination | 8
|  | Procure Consultant | 0
|  | Design Complete | 22.918
|  | Environmental Clearance for Letting Milestone | #N/A
|  | Railroad Coordination Complete | #N/A
|  | ROW Possessed Milestone | 0
|  | Utilities Adjusted Milestone | 0
|  | Total Duration | #N/A
Formulas:
Forecast Start Date = [Forecast Start Date, row above]
Forecast Start Date = [Forecast Finish Date, row above]
Forecast Finish Date = EDATE([Forecast Start Date],[Months])
Forecast Finish Date = MAX(IFERROR(EDATE(G31,3),0), IF(N([Months])=0, [Forecast Start Date, row above], EDATE([Forecast Start Date], N([Months]))))

## LPA Schedule Tool- Schematic
Local Government Preliminary Scheduling Tool- Schematic
AFA Process | Criteria
Has the AFA been completed? | FALSE
Procure Consultant | Criteria
Has the consultant selection process been approved by TxDOT
Schematic/Preliminary Design | Criteria
Check if schematic phase needed? | FALSE
Design | Criteria
Project Scope
Check if this a FHWA Major Project or is a Value Engineering Study is proposed | FALSE
ROW | Criteria
Type of Parcels Checklist
Easements | FALSE
Undeveloped Acreage | FALSE
Residential | FALSE
Commercial | FALSE
Industrial | FALSE
How many parcels will there be?
Check if pushback is anticipated | FALSE
Will the ROW phase be managed by TxDOT? | FALSE
Utilities | Criteria
Type of Utilities Checklist
Fiber Optic | FALSE
Gas | FALSE
Water | FALSE
Overhead Transmission | FALSE
Duct Bank | FALSE
How many total utilities provider's fracilities will be impacted by this project?
Will the utilities phase be managed by TxDOT? | FALSE
Railroad
Railroad Present
Will the railroad phase be managed by TxDOT? | FALSE
Environmental Complexity Selection | Criteria
Environmental Documentation Needed
Will the environmental clearance phase be managed by TxDOT? | FALSE

## Schedule Output- Schematic
Local Government Preliminary Scheduling Tool
Schematic
Basic Project Information
Project Name | 0
Sponsor (Owner) | ZYX County
County | XYZ
CSJ | 0
Roadway/ Structure ID | 0
Project Limits | 0
Project Length | 0
Project Location | Metropolitan
LG Risk Score | D
AADT Traffic Count/ Count Year | 45,000 - 2024
Estimated Construction Cost | 10000000
Project Initiation Date | 2025-01-01
Local Government Preliminary Scheduling Tool
Ref # | OPC Activity ID | Recommended Schedule | Months | Forecast Start Date | Forecast Finish Date | Predecessors | Successors
1 | START | Start Milestone | 0 | 2025-01-01 |  |  | 2
2 | AFACOMP | AFA Complete | 8 | 2025-01-01 | 2025-09-01 | 1 | 3
3 | PROCON | Procure Consultant | #N/A | 2025-09-01 | #N/A | 2 | 5,9
4 | SCHAPP | Schematic/Preliminary Design | #N/A | #N/A | #N/A | 3FF,9FF | 5SS
5 | A1000 | Start Design Date | 0 | #N/A |  | 4SS | 6,9SS
6 | DES030 | PS&E 30% Complete Milestone | #N/A | #N/A | #N/A | 5 | 7,10,11,12
7 | DES060 | PS&E 60% Complete Milestone | #N/A | #N/A | #N/A | 6 | 8
8 | DES095 | PS&E 95% Complete Milestone (Optional) | #N/A | #N/A | #N/A | 7 | 13
9 | ENVCLR | Environmental Clearance for Letting Milestone | #N/A | 2025-09-01 | #N/A | 3 | 4FF
10 | RRCERT | Railroad Coordination Complete | #N/A | #N/A | #N/A | 6 | 14
11 | ROWCERT | ROW Possessed Milestone | 0 | #N/A | #N/A | 6 | 9FF*,14
12 | UTLCERT | Utilities Adjusted Milestone | 0 | #N/A | #N/A | 6 | 14
13 | DES1000 | PS&E 100% Complete Milestone | #N/A | #N/A | #N/A | 8 | 14
14 | RTL1000 | Ready to Let Milestone | 0 | #N/A | #N/A | 9,10,11,12,13
|  | Total | #N/A
|  | AFA Coordination | 8
|  | Procure Consultant | #N/A
|  | Design Complete | #N/A
|  | Environmental Clearance for Letting Milestone | #N/A
|  | Railroad Coordination Complete | #N/A
|  | ROW Possessed Milestone | #N/A
|  | Utilities Adjusted Milestone | #N/A
|  | Total Duration | #N/A
Formulas:
Forecast Start Date = [Forecast Start Date, row above]
Forecast Start Date = [Forecast Finish Date, row above]
Forecast Finish Date = EDATE([Forecast Start Date],[Months])
Forecast Finish Date = IF([Months]=0,[Forecast Start Date, row above],(MAX(EDATE([Forecast Start Date],[Months]),G32)))

## Gantt Chart
Local Government Preliminary Scheduling Tool
LGP Preliminary Tool Gantt Chart- No Schematic Phase
Project Start
AFA Complete
Initiation
Procurement Complete
Procurement
|  |  | PS&E Start | PS&E 30%/Project Planning Complete | PS&E 60% | PS&E 95% |  | PS&E Complete
Design
ROW Clear
ROW
Railroad Coord. Complete
Railroad
Utilities Clear
Utilities
ENV Complete
ENV
Ready to Let
LGP Preliminary Tool Gantt Chart- Schematic Phase
Project Start
AFA Complete
Initiation
Procurement Complete
Procurement
Prelim/Schematic Complete
Prelim/Schematic
[5 empty] | PS&E Start | PS&E 30%/Project Planning Complete | PS&E 60% |  | PS&E 95% |  | PS&E Complete
Design
ROW Clear
ROW
Railroad Coord. Complete
Railroad
Utilities Clear
Utilities
ENV Complete
ENV
Ready to Let
Ready To Let Milestone is only achieved once PS&E Complete, ROW Clear, Railroad Coord. Complete, Utilities Clear, and ENV Complete milestones have all been met. Completion of each milestone may vary. The total project time is based on the Longest path to reach Ready to Let.
Ready To Let Milestone is only achieved once PS&E Complete, ROW Clear, Railroad Coord. Complete, Utilities Clear, and ENV Complete milestones have all been met. Completion of each milestone may vary. The total project time is based on the Longest path to reach Ready to Let.
Data collection time represents efforts taken to prepare for Environmental Documentation. This time is not part of the documentation process.
This time represents the Environmental Documentation Process that is being done concurrent with the Schematic Development. Additional time is shown in the PS&E Phase for updates to the Env. Document if needed. The durations calcualted by this tool does not include time for any updates to the Env. Document.

## Criteria
Local Government Preliminary Scheduling Tool
Risk Score | Standard Timeline (Months)
A | 0
B | 0
C | 6
D | 12
AFA Process Complete? | Standard Timeline (Months)
Yes | 0
No | 8
Procure Consultant | Standard Timeline (Months)
No, the process has not been approved | 7
Yes, the process has been approved | 4
Non-federal procurement process. Consultant Not Yet Selected | 2
Yes, the process has been approved and a consultant has been procured | 0
Non-federal procurement process- Consultant Selected | 0
Project Scope | Standard Design Timeline (Months) | Standard Schematic Timeline (Months)
Bridge Maintenance (if Cat 6 funded) | 6
Bridge Replacement | 18
Bridge Widening or Rehabilitation | 12
Convert Non-Freeway To Freeway | 18 | 12
Culvert & Storm Drainage Work | 6
Freeway Operational Improvements | 6 | 12
Feasibility Studies | 9
Interchange (New or Reconstructed) | 24 | 16
Intersection & Operational Improvements | 9 | 9
Landscape & Scenic Enhancement | 6
New Location Freeway | 24 | 16
New Location Non-Freeway | 18 | 16
Overlay | 6
Pedestrian, Sidewalks and Curb Ramps | 9
Rehabilitation of Existing Road | 9
Restoration | 9
Rail Hwy Crossing Signals/Structures | 9
Rail Line | 12
Seal Coat | 6
Safety Improvement Projects | 6
Super-2 Highway | 12
Traffic Control Devices | 6
Widen Freeway | 18 | 16
Widen Non-Freeway | 12 | 16
Bicycle Infrastructure Improvements | 12
Traffic Signal | 6
Hazard Elimination & Safety | 6
Project Location | Multiplier
Rural | 0.8
Urban | 1
Metropolitan | 1.2
Is this a FHWA Major Project or is a value engineering study required? | Duration (Months)
Yes | 3
No | 0
ROW: Type of Parcels | Duration (Months)
Easements | 12
Undeveloped Acreage | 12
Residential | 18
Commercial | 24
Industrial | 24
ROW: Number of Parcels | Multiplier
1-5 | 1
6-10 | 1.2
11-15 | 1.35
> 15 | 1.5
Anticipated Pushback? | Multiplier
Yes | 1.5
No | 1
Utilities: Type of utilities | Duration (Months)
Fiber Optic | 18
Gas | 18
Water | 18
Overhead Transmission | 24
Duct Bank | 24
ROW: Number of utilities | Multiplier
1-5 | 1
6-10 | 1.2
11-15 | 1.35
> 15 | 1.5
Railroad Present | Months (Months)
None | 0
Within 51-500 ft of Railroad ROW | 12
Within 50 ft. at-grade crossing | 18
Work on Railroad ROW | 24
Environmental Clearance | Standard Timeline (months)
CE | 6
EA | 12
EIS | 24