## Sheet1
Northpark Drive Reconstruction Project Development and Implementation Timeline
Calendar Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4 | 2022-1 | 2022-2 | 2022-3 | 2022-4 | 2023-1
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
AFA Execution | bar: Calendar Year and Quarter 2020-3 to Calendar Year and Quarter 2020-4
Procure Consultants | bar: Calendar Year and Quarter 2020-3 to Calendar Year and Quarter 2020-4
Kick Off | bar: Calendar Year and Quarter 2021-1
30% | bar: Calendar Year and Quarter 2021-2
60% | bar: Calendar Year and Quarter 2021-3 to Calendar Year and Quarter 2021-4
90% | bar: Calendar Year and Quarter 2022-1
95%/100% | bar: Calendar Year and Quarter 2022-2 to Calendar Year and Quarter 2022-3
NEPA | bar: Calendar Year and Quarter 2021-2 to Calendar Year and Quarter 2021-4
Utility Coordination/Relocation | bar: Calendar Year and Quarter 2021-2 to Calendar Year and Quarter 2022-4
ROW Acquisition | bar: Calendar Year and Quarter 2022-1 to Calendar Year and Quarter 2022-4
Letting | bar: Calendar Year and Quarter 2023-1