## Sheet1
Calendar Year and Quarter
Project Phase | 2019-1 | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4 | YOI 2021
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-1 to Calendar Year and Quarter 2019-2
AFA Execution
Procure Consultants | bar: Calendar Year and Quarter 2019-4
Kick Off | bar: Calendar Year and Quarter 2020-1
30% | bar: Calendar Year and Quarter 2020-2
60% | bar: Calendar Year and Quarter 2020-3
90% | bar: Calendar Year and Quarter 2020-4
95%/100% | bar: Calendar Year and Quarter 2021-1
NEPA | bar: Calendar Year and Quarter 2020-1 to Calendar Year and Quarter 2020-3
Utility Coordination/Relocation | bar: Calendar Year and Quarter 2020-1 to Calendar Year and Quarter 2021-1
ROW Acquisition
Letting | bar: Calendar Year and Quarter 2021-2