## Project Assumptions and Inputs
State of Good Repair |  |  | Conversion factors
| Project | Repair Solution | 5280 | feet/mile | 0.11111 | square yards in 1 square foot
Alternatives | Reconstruction | Concrete Base Repair and Overlay (Concrete), Mill and Overlay (Asphalt) | Inflation Rate |  | 2.8% | OMB-94 | https://obamawhitehouse.archives.gov/omb/circulars_a094/a94_appx-c.
|  |  | Wage inflation |  | 1.2% | HGAC template
Note: repair solution to be determined by David Rodgers |  |  | Residual life factor |  | 0% | Zeroed out for now, could apply same inflation rate if needed.
PROJECT INPUTS
RECONSTRUCTION
PROJECT USER COST |  | Get from Project Manager!
Length of Roadway (miles) | 0.96 | Total length being reconstructed; replace w/actual value
Length of Roadway (feet) | 5068.8
Lane Width (feet) | 12 | Replace with actual value
Number of lanes | 2 | Replace with actual value
Traffic control and mobilization | 15% | Value from previous analysis
Design fee | 10% | From David Rodgers/Jim meeting 7/17
Service life of improvement | 40 | Number of years that treatment will last. Reconstruction is assumed to last the full 20 year analysis period.
USER COST
Speed limit | 45 | mph on roadway; replace with actual value
Vehicle occupancy | 1.25 | Appears to be default for HGAC (in benefits analyses)
Construction days/mile | 240 | Assume 240 days/mile if no better value; ask PM or engineer if there is a better estimate.
Value of travel time (VoTT) | 16.6866 | 2018$; used $16.10 from H-GAC spreadsheet (2015) inflated to 2018. Taken originally from TIGER 2014
2018 AADT/TDF Volumes | 15092 | Derived from HGAC model (without the project) or traffic counts (if available). Replace with actual value. GIMS and TxDOT are other sources of counts.
AADT increase/year | 0.836% | Derived from HGAC model. Use future year 2040 to calculate growth rate. Replace with actual value
Travel time during construction (hours) | 0.042667 | Calculated from the speed limit * length of roadway * doubling travel time. Doubling value decided on at meeting 7/17
REPAIR SOLUTION INPUTS
Could be base repair and overlay, mill and overlay, etc.
Length of Roadway (miles) | 0.96 | Total length of corridor
Length of Roadway (feet) | 5068.8
Lane Width (feet) | 12 | Replace with actual value
Number of lanes | 2 | Replace with actual value
Traffic control and mobilization | 15% | Value from previous analysis
Design fee | 6% | David/Jim suggestion
Service life of improvement: concrete | 15 | Number of years that treatment will last. Concrete is assumed to last 15 years. City of Houston PPT says 12-18 years
Service life of improvement: asphalt | 10 | Number of years that treatment will last. Mill and overlay is assumed to last 10 years. City of Houston PPT says 6-12 years
USER COST |  | 5049.6
Length of Roadway (miles) | 0.96 | Total length needing repair; replace with actual value from either % repaired for Mill and Overlay or Concrete
Speed limit | 45 | mph on roadway; replace with actual value
Vehicle occupancy | 1.25 | Appears to be default for HGAC (in benefits analyses)
Rehabilitation days | 60 | Assume 1/4 of the 240 used in prior spreadsheets (value decided on at meeting 7/17)
Value of travel time (VoTT) | 16.6866 | 2018$; used $16.10 from H-GAC spreadsheet (2015) inflated to 2018. Taken originally from TIGER 2014
2018 AADT/TDF Volumes | 15092 | Derived from HGAC model (without the project) or traffic counts (if available). Replace with actual value. GIMS and TxDOT are other sources of counts.
AADT increase/year (%) | 0.0083605 | Derived from HGAC model. Use future year to calculate growth rate. Replace with actual value
Travel time during construction (hours) | 0.042667 | Calculated from the speed limit * length of roadway * doubling travel time. Doubling value decided on at meeting 7/17

## Construction costs
Construction costs used in these analyses
Project Alternative | Unit Cost ($)
Obtain from PM, do not calculate. ASSUMES 2017 DOLLARS.
Concrete Base Repair
Concrete Base Repair (square yard) | 205 | Assume each panel is 50' * 12' = 67 SY so $13,735/panel
1 Square foot = 0.11111 square yard | 0.11111
Percent of concrete base needing repair | 20% | Replace with field observation or PM information
Mill and Overlay for Asphalt
Mill and Overlay Cost ($/lane mile) | 174640 | TxDOT low bid, 6/30/17. See DR email, 7/19/27
Percent of Pavement base needing repair | 100% | Replace with field observation or PM information
https://www.houstontx.gov/council/committees/tti/20140513/Maintaining_Houston_Streets.pdf

## SOGR and User Costs
Reconstruction Costs
Removing concrete base and new pavement (concrete):
2018 | 0 | For residual life benefit calculation
2021 | 0 | Input cost of the project, inflated to project year in this cell (assuming cost is in 2017$).
2030
2040 | 0 | This assumes half life left in 2040, applied residual life factor based on 2018$
User costs:
2021 | 3288398.0534 | Assumes AADT growth from 2018-2020 and wage increase
Repair Costs
Concrete Base Repair: | [5 empty] | User costs:
Assumes AADT growth from 2015-2020 and wage increase
Assumes AADT growth from 2015-2035 and wage increase
Mill and Overlay: | [5 empty] | User costs:
2020 | 444046.0396 | Inflated to project year in this cell |  |  |  | 2020 | 805615.972 | Assumes AADT growth from 2015-2020 and wage increase
2030 | 585273.8868 | Includes a 2.8% inflation rate for the 10 years |  |  |  | 2030 | 986486.8494 | Assumes AADT growth from 2015-2030 and wage increase
Round of repairs in 2040 not added into analysis
Summary Costs
| Alternative A: Reconstruct/Project |  | Alternative B: Repair/Non-Project |  | Alternative B: Repair/Non-Project
|  |  | CONCRETE |  | MILL AND OVERLAY
| Construction | User Cost | Construction | User Cost | Construction | User Cost
2021 | 0 | 3288398.0534 | 0 | 0 | 444046.0396 | 805615.972
2030 | 0 |  |  |  | 585273.8868 | 986486.8494
0 |  |  | 0 | 0
2040 | 0 |  | 0
Note: If you only use one treatment, delete out the values in this summary table here (cells 26 down)

## Discounted Costs
Summary Costs | [7 empty] | (Not discounted)
| Alternative A: Reconstruct/Project |  | Alternative B: Repair/Non-Project |  | Alternative B: Repair/Non-Project
|  |  | CONCRETE |  | MILL AND OVERLAY
| Construction | User Cost | Construction | User Cost | Construction | User Cost
2021 | 0 | 3288398.0534 | 0 | 0 | 444046.0396 | 805615.972 | 1249662.0116
2030 | 0 | 0 | 0 | 0 | 585273.8868 | 986486.8494 | 1571760.7362
0 | 0 | 0 | 0 | 0 | 0 | 0
2040 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 3288398.0534 | 0 | 0 | 1029319.9264 | 1792102.8215
SOGR BENEFIT
2821422.7479 | SOGR - repair costs, not discounted
-466975.3055 | Delta between repair and reconstruct (reference only)
RESIDUAL LIFE BENEFIT
0 | Not discounted; separate line item
3% Discount Rate | [7 empty] | 3% | Discount Rate
| Alternative A: Reconstruct/Project |  | Alternative B: Repair/Non-Project |  | Alternative B: Repair/Non-Project
|  |  | CONCRETE |  | MILL AND OVERLAY
| Construction | User Cost | Construction | User Cost | Construction | User Cost
2021 | 0 | 3192619.4693 | 0 | 0 | 431112.6598 | 782151.4291
2030 | 0 | 0 | 0 | 0 | 448563.6998 | 756060.0276
0 | 0 | 0 | 0 | 0 | 0 | 0
2040 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 3192619.4693 | 0 | 0 | 879676.3597 | 1538211.4568
SOGR BENEFIT
2417887.8165 | Repair costs only - this is what the SOGR is!
-774731.6529 | Delta between repair and reconstruct scenario (reference only)
RESIDUAL LIFE BENEFIT
0 | 3% discount; separate line item
7% Discount Rate | [7 empty] | 7% | Discount Rate
| Alternative A: Reconstruct/Project |  | Alternative B: Repair/Non-Project |  | Alternative B: Repair/Non-Project
|  |  | CONCRETE |  | MILL AND OVERLAY
| Construction | User Cost | Construction | User Cost | Construction | User Cost
2021 | 0 | 3073269.2088 | 0 | 0 | 414996.2987 | 752912.1234
2030 | 0 | 0 | 0 | 0 | 318350.2157 | 536583.484
0 | 0 | 0 | 0 | 0 | 0 | 0
2040 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 3073269.2088 | 0 | 0 | 733346.5144 | 1289495.6074
SOGR BENEFIT
2022842.1218 | Repair costs only - this is what SOGR is!
-1050427.087 | Delta between repair and reconstruct scenario (reference only)
RESIDUAL LIFE BENEFIT
0 | 7% discount; separate line item