## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  |  | Data entered by the sponsors | Brazoria | No
Project Title | Meadowglen West Complete Streets Project |  |  |  | Data populated/calculated based on inputs | Chambers | No
County | Harris |  |  |  |  | Fort Bend | No
Facility/Street Name | Meadowglen West |  |  |  |  | Galveston | No
TDCs Requested (Y/N) | No |  |  |  |  | Harris | Yes
[6 empty] | Liberty | No
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  |  | Montgomery | No
[6 empty] | Waller | No
Planning/Environmental | 2019-04-01 | 2019-09-01 | 0
Design | 2020-04-01 | 2020-12-01 | 859.923 | 859923
Property/ROW Acquisition | 2019-10-01 | 2020-09-01 | 0
Utility Relocation | 2019-04-01 | 2020-09-01 | 0
Construction | 2020-12-01 | 2022-02-01 | 4890.27 | 4890270
Federal Requested |  |  | 5750.193
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 18828.745 | 18828745
Other |  |  | 0
Total Match |  |  | 18828.745
Total Project Cost ('000s) |  |  | 24578.938