## Sheet1
Eastwood Intermodal Terminal Project Development and Implementation Timeline
Calendar Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4 | 2022-1
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
Transfer Funds to FTA | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
Procure Consultants | Calendar Year and Quarter 2019-2: COMPLETE
Kick Off | Calendar Year and Quarter 2019-2: COMPLETE
30% | Calendar Year and Quarter 2019-2: COMPLETE
60% | Calendar Year and Quarter 2019-2: COMPLETE
90% | Calendar Year and Quarter 2019-2: COMPLETE
95%/100% | Calendar Year and Quarter 2019-2: COMPLETE
NEPA | Calendar Year and Quarter 2019-2: COMPLETE
Utility Coordination/Relocation | Calendar Year and Quarter 2019-2: COMPLETE
ROW Acquisition | Calendar Year and Quarter 2019-2: COMPLETE
RFP Capital Lease | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2020-1
Execute Capital Lease Agreement | bar: Calendar Year and Quarter 2020-2