## CLKS
New Clear Lake Road Bridge: Access and Mobility Improvements
Calendar Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4 | 2022-1
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
AFA | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
Procure Consultants | bar: Calendar Year and Quarter 2020-2
Kick Off | bar: Calendar Year and Quarter 2020-3
30% | bar: Calendar Year and Quarter 2020-4
60% | bar: Calendar Year and Quarter 2021-1
90% | bar: Calendar Year and Quarter 2021-2
95%/100% | bar: Calendar Year and Quarter 2021-3 to Calendar Year and Quarter 2021-4
NEPA | bar: Calendar Year and Quarter 2020-3 to Calendar Year and Quarter 2021-2
Utility Coordination/Relocation | Calendar Year and Quarter 2019-2: NOT APPLICABLE
ROW Acquisition | Calendar Year and Quarter 2019-2: NOT APPLICABLE
Letting | bar: Calendar Year and Quarter 2022-1