## Holman
Holman St Reconstruction and Bike/Ped Improvements
Fiscal Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2
TIP/STIP Amendments | bar: Fiscal Year and Quarter 2019-2 to Fiscal Year and Quarter 2019-3
AFA Execution | bar: Fiscal Year and Quarter 2019-4 to Fiscal Year and Quarter 2020-1
Procure Consultants | bar: Fiscal Year and Quarter 2020-1
Kick Off | bar: Fiscal Year and Quarter 2020-1
30% | bar: Fiscal Year and Quarter 2020-1
60% | bar: Fiscal Year and Quarter 2020-2
90% | bar: Fiscal Year and Quarter 2020-3
95%/100% | bar: Fiscal Year and Quarter 2020-4 to Fiscal Year and Quarter 2021-1
NEPA | bar: Fiscal Year and Quarter 2020-2 to Fiscal Year and Quarter 2020-4
Utility Coordination/Relocation | bar: Fiscal Year and Quarter 2020-1 to Fiscal Year and Quarter 2020-4
Letting | bar: Fiscal Year and Quarter 2021-2