## Sheet1
West Alabama Multimodal Enhancement Project Path Project Development and Implementation Timeline
Calendar Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
FTA Transfer | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
Procure Consultants | Calendar Year and Quarter 2019-2: COMPLETED
Kick Off | Calendar Year and Quarter 2019-2: COMPLETED
30% | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
60% | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
90% | bar: Calendar Year and Quarter 2020-2
95%/100% | bar: Calendar Year and Quarter 2020-3
NEPA | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
Utility Coordination/Relocation | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2020-3
ROW Acquisition | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2021-3
Letting | bar: Calendar Year and Quarter 2021-4