## Sheet1
Calendar Year and Quarter
Project Phase | 2019-1 | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | FY2020
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-1 to Calendar Year and Quarter 2019-2
AFA Execution
Procure Consultants | bar: Calendar Year and Quarter 2019-2
Kick Off | bar: Calendar Year and Quarter 2019-3
30% | bar: Calendar Year and Quarter 2019-4
60% | bar: Calendar Year and Quarter 2020-1
90% | bar: Calendar Year and Quarter 2020-2
95%/100% | bar: Calendar Year and Quarter 2020-3
NEPA | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-4
Utility Coordination/Relocation | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-4
ROW Acquisition
Letting | bar: Calendar Year and Quarter 2020-4