## Sheet1
FM 1314 Extension Project Development and Implementation Timeline
Calendar Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4 | 2022-1 | 2022-2
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
AFA Execution | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
Procure Consultants | bar: Calendar Year and Quarter 2020-2
Kick Off | bar: Calendar Year and Quarter 2020-3
30% | bar: Calendar Year and Quarter 2020-4
60% | bar: Calendar Year and Quarter 2021-1
90% | bar: Calendar Year and Quarter 2021-2
95%/100% | bar: Calendar Year and Quarter 2021-3 to Calendar Year and Quarter 2022-1
NEPA | bar: Calendar Year and Quarter 2020-3 to Calendar Year and Quarter 2021-1
Utility Coordination/Relocation | bar: Calendar Year and Quarter 2020-3 to Calendar Year and Quarter 2022-1
ROW Acquisition | bar: Calendar Year and Quarter 2021-2 to Calendar Year and Quarter 2022-1
Letting | bar: Calendar Year and Quarter 2022-2