## Sheet1
Calendar Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
Flex to FTA | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
Procure Consultants | bar: Calendar Year and Quarter 2020-2
Kick Off - Completed | bar: Calendar Year and Quarter 2020-3
60% | bar: Calendar Year and Quarter 2020-4
90% | bar: Calendar Year and Quarter 2021-1
95%/100% | bar: Calendar Year and Quarter 2021-2
NEPA | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
Letting | bar: Calendar Year and Quarter 2021-3