## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | David Memorial Extension |  |  | Data populated/calculated based on inputs | Chambers | No
County | Montgomery |  |  |  | Fort Bend
Facility/Street Name | David Memorial Extension |  |  |  | Galveston
TDCs Requested (Y/N) | Yes |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  | Montgomery
Waller
Planning/Environmental | 2019-01-01 | 2020-06-01 | 150
Design | 2019-01-01 | 2020-12-01 | 620
Property/ROW Acquisition | 2019-07-01 | 2019-12-01 | 780
Utility Relocation | 2020-01-01 | 2020-12-01 | 80
Construction | 2021-04-01 | 2022-04-01 | 5370
Federal Requested |  |  | 7000
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 2000
Other |  |  | 0
Total Match |  |  | 2000
Total Project Cost ('000s) |  |  | 9000