## Sheet1
Northwest Transit Center / Memorial Park / Heights Shared Use Path Project Development and Implementation Timeline
Calendar Year and Quarter
Project Phase | 2021-1 | 2021-2 | 2021-3 | 2021-4 | 2022-1 | 2022-2 | 2022-3 | 2022-4 | 2023-1 | 2023-2 | 2023-3 | 2023-4 | 2024-1
LONP (Pre Award Authority) | Calendar Year and Quarter 2021-1: COMPLETED 2019-1
TIP/STIP Amendments | bar: Calendar Year and Quarter 2021-1 to Calendar Year and Quarter 2021-2
Transfer to FTA/Execute Grant | bar: Calendar Year and Quarter 2021-3 to Calendar Year and Quarter 2021-4
Procure Consultants | bar: Calendar Year and Quarter 2022-1
Kick Off | bar: Calendar Year and Quarter 2022-2
30% | Calendar Year and Quarter 2021-1: COMPLETE
60% | bar: Calendar Year and Quarter 2022-3 to Calendar Year and Quarter 2022-4
90% | bar: Calendar Year and Quarter 2023-1
95%/100% | bar: Calendar Year and Quarter 2023-2 to Calendar Year and Quarter 2023-4
NEPA | Calendar Year and Quarter 2021-1: COMPLETE
Utility Coordination/Relocation | bar: Calendar Year and Quarter 2022-2 to Calendar Year and Quarter 2023-3
ROW Acquisition | Calendar Year and Quarter 2021-1: COMPLETE
Letting | bar: Calendar Year and Quarter 2024-1