## Tuckerton Road West
Bridgeland Management District: Tuckerton Road West Connector
Fiscal Year and Quarter
Project Phase |  | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4 | 2022-1 | 2022-2 | 2022-3 | 2022-4 | 2023-1
TIP/STIP Amendments | bar: Fiscal Year and Quarter 2019-2 to Fiscal Year and Quarter 2019-3
AFA Execution | bar: Fiscal Year and Quarter 2019-4 to Fiscal Year and Quarter 2020-1
Procure Consultants | bar: Fiscal Year and Quarter 2019-2 to Fiscal Year and Quarter 2019-3
Kick Off | bar: Fiscal Year and Quarter 2020-2
30% | bar: Fiscal Year and Quarter 2020-3
60% | bar: Fiscal Year and Quarter 2020-4
90% | bar: Fiscal Year and Quarter 2021-1
95%/100% | bar: Fiscal Year and Quarter 2021-2 to Fiscal Year and Quarter 2021-3
NEPA | bar: Fiscal Year and Quarter 2020-2 to Fiscal Year and Quarter 2021-1
Utility Coordination/Relocation | Not Required
ROW Acquisition | Not Required
Letting | bar: Fiscal Year and Quarter 2021-4
Construction | bar: Fiscal Year and Quarter 2022-1 to Fiscal Year and Quarter 2022-4
Implementation | bar: Fiscal Year and Quarter 2023-1