## Sheet1
Calendar Year and Quarter
Project Phase | 2019-1 | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
AFA Execution - NA | bar: Calendar Year and Quarter 2019-3 to Calendar Year and Quarter 2019-4
Letter of No Prejudice | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
Flex to FTA | bar: Calendar Year and Quarter 2019-3 to Calendar Year and Quarter 2019-4
Procure Consultants - Completed
Kick Off - Completed
30% | bar: 2019-1
60% | bar: 2019-1 to Calendar Year and Quarter 2019-2
90% | bar: Calendar Year and Quarter 2019-2
95%/100% | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
NEPA | bar: 2019-1 to Calendar Year and Quarter 2019-2
Utility Coordination/Relocation - NA
ROW Acquisition - NA
Letting | bar: Calendar Year and Quarter 2019-3
Construction | bar: Calendar Year and Quarter 2019-3 to Calendar Year and Quarter 2020-3