## Sheet1
Waco St. Extension amd Reconstruction Project Development and Implementation Timeline
Calendar Year and Quarter
Project Phase | 2019-2 | 2019-3 | 2019-4 | 2020-1 | 2020-2 | 2020-3 | 2020-4 | 2021-1 | 2021-2 | 2021-3 | 2021-4 | 2022-2 | 2022-3 | 2022-4 | 2023-1 | 2023-2 | 2023-3 | 2023-4
TIP/STIP Amendments | bar: Calendar Year and Quarter 2019-2 to Calendar Year and Quarter 2019-3
AFA Execution | bar: Calendar Year and Quarter 2019-4 to Calendar Year and Quarter 2020-1
Procure Consultants | bar: Calendar Year and Quarter 2020-2
Kick Off | bar: Calendar Year and Quarter 2020-3
30% | bar: Calendar Year and Quarter 2020-4
60% | bar: Calendar Year and Quarter 2021-1
90% | bar: Calendar Year and Quarter 2021-2 to Calendar Year and Quarter 2021-3
95%/100% | bar: Calendar Year and Quarter 2021-4 to Calendar Year and Quarter 2022-3
NEPA | bar: Calendar Year and Quarter 2020-3 to Calendar Year and Quarter 2021-1
Utility Coordination/Relocation | bar: Calendar Year and Quarter 2020-3 to Calendar Year and Quarter 2021-2
ROW Acquisition | bar: Calendar Year and Quarter 2021-2 to Calendar Year and Quarter 2022-3
Letting | bar: Calendar Year and Quarter 2022-4
Construction | bar: Calendar Year and Quarter 2023-1 to Calendar Year and Quarter 2023-4