## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | Bailey Road Expansion (Veterans Dr to Main/SH 35) |  |  |  | Data populated/calculated based on inputs | Chambers | No
County | Brazoria |  |  |  |  | Fort Bend
Facility/Street Name | Bailey Road |  |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  |  | Montgomery
Waller
Planning/Environmental | 11/2019 | 5/2020
Design | 7/2019 | 1/2021
Property/ROW Acquisition | N/A | N/A
Utility Relocation | 1/2020 | 7/2020 | 96
Construction | 4/2021 | 8/2022 | 14452
Federal Requested |  |  | 14548
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 3637 | 3637
Other |  |  | 0
Total Match |  |  | 3637
Total Project Cost ('000s) |  |  | 18185