## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information |  |  |  | Data entered by the sponsors | Brazoria | Yes
Project Title | Gulf Bank Road |  |  | Data populated/calculated based on inputs | Chambers | No
County | Harris |  |  |  | Fort Bend
Facility/Street Name | Gulf Bank Road |  |  |  | Galveston
TDCs Requested (Y/N) | No |  |  |  | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  | Montgomery
Waller
Planning/Environmental | 2018-09-03 | 2021-09-03 | 0
Design | 2019-12-09 | 2020-12-09 | 0
Property/ROW Acquisition | 2021-09-06 | 2023-04-03 | 0
Utility Relocation | 2021-06-11 | 2023-04-03 | 0
Construction | 2023-05-15 | 2025-05-13 | 15559.9452
Federal Requested |  |  | 15559.9452
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 3889.9863
Other |  |  | 0
Total Match |  |  | 3889.9863
Total Project Cost ('000s) |  |  | 19449.9314