## Instructions
Instructions:
1. On the "Project Budget" tab, fill in all "blue" shaded sections. All project costs must be entered in 2018 $ values. Costs will be inflated to the programming year values by HGAC staff.
2. Total Federal requested and the total match amounts are populated based on the input values

## Project Budget
All project costs must be entered in 2018 $s. Costs will be inflated to prgramming year by HGAC staff.
County
Project Information | [5 empty] | Data entered by the sponsors | Brazoria | Yes
Project Title | Waco St Extension and Reconstruction |  |  |  |  | Data populated/calculated based on inputs | Chambers | No
County | Liberty | [5 empty] | Fort Bend
Facility/Street Name | Waco Street | [5 empty] | Galveston
TDCs Requested (Y/N) | No | [5 empty] | Harris
Liberty
Project Costs ('000s) | Estimated Start Date | Estimated Completion Date | Project Total (000s) |  |  |  | Montgomery
|  |  |  | 100% | 80% |  | Waller
Planning/Environmental | 2020-07-01 | 2021-03-31 | 80 | 100000 | 80000
Design | 2020-10-01 | 2022-09-30 | 687.5704 | 859463 | 687570.4
Property/ROW Acquisition | 2021-04-01 | 2022-09-30 | 680 | 850000 | 680000
Utility Relocation | 2020-07-01 | 2021-06-30 | 0 |  | 0
Construction | 2023-01-01 | 2023-12-31 | 6925.168 | 8656460 | 6925168
Federal Requested |  |  | 8372.7384 | 10465923 | 8372738.4
Local/State Match ('000s)
State |  |  | 0
Local - General Revenue |  |  | 3769.1936 | 3769193.6
Other |  |  | 0
Total Match |  |  | 3769.1936 |  | 31.04%
12141932
Total Project Cost ('000s) |  |  | 12141.932