## Project Assumptions and Inputs
State of Good Repair |  |  | Conversion factors
| Project | Repair Solution | 5280 | feet/mile | 0.11111 | square yards in 1 square foot
Alternatives | Reconstruction | Concrete Base Repair and Overlay (Concrete) & Mill and Overlay (Asphalt) | Inflation Rate |  | 2.8% | OMB-94 | https://obamawhitehouse.archives.gov/omb/circulars_a094/a94_appx-c.
|  |  | Wage inflation |  | 1.2% | HGAC template
Note: repair solution to be determined by David Rodgers
PROJECT INPUTS
RECONSTRUCTION
PROJECT COST |  | Get from Project Manager!
Length of Roadway (miles) | 2.25 | Total length being reconstructed; replace w/actual value
Length of Roadway (feet) | 11880
Roadway Width (feet) | 11 | Replace with actual value
Number of lanes | 4 | Replace with actual value
Traffic control and mobilization | 15% | Value from previous analysis
Design fee | 10% | From David Rodgers/Jim meeting 7/17
Service life of improvement | 40 | Number of years that treatment will last. Reconstruction is assumed to last the full 20 year analysis period.
USER COST
Speed limit | 35 | mph on roadway; replace with actual value
Vehicle occupancy | 1.25 | Appears to be default for HGAC (in benefits analyses)
Construction days/mile | 240 | Assume 240 days/mile if no better value; ask PM or engineer if there is a better estimate.
Value of travel time (VoTT) | 16.4887 | 2017$; used $16.10 from H-GAC spreadsheet (2015) inflated to 2017. Taken originally from TIGER 2014
2015 AADT | 18670 | Derived from HGAC model (without the project) or traffic counts (if available). Replace with actual value
AADT increase/year | 0.48% | Derived from HGAC model. Use future year 2040 to calculate growth rate. Replace with actual value
Travel time during construction (hours) | 0.12857 | Calculated from the speed limit * length of roadway * doubling travel time. Doubling value decided on at meeting 7/17
REPAIR SOLUTION INPUTS
Could be base repair and overlay, mill and overlay, etc.
Length of Roadway (miles) | 2.25 | Total length needing repair; replace with actual value
Length of Roadway (feet) | 11880
Roadway Width (feet) | 11 | Replace with actual value
Number of lanes | 4 | Replace with actual value
Traffic control and mobilization | 15% | Value from previous analysis
Design fee | 6% | David/Jim suggestion
Service life of improvement: concrete | 15 | Number of years that treatment will last. Concrete is assumed to last 15 years. City of Houston PPT says 12-18 years
Service life of improvement: asphalt | 10 | Number of years that treatment will last. Mill and overlay is assumed to last 10 years. City of Houston PPT says 6-12 years
USER COST
Speed limit | 35 | mph on roadway; replace with actual value
Vehicle occupancy | 1.25 | Appears to be default for HGAC (in benefits analyses)
Rehabilitation days | 60 | Assume 1/4 of the 240 used in prior spreadsheets (value decided on at meeting 7/17)
Value of travel time (VoTT) | 16.49 | 2017$; used $16.10 from H-GAC spreadsheet (2015) inflated to 2017. Taken originally from TIGER 2014
2015 AADT | 18670 | Derived from HGAC model (without the project) or traffic counts (if available). Replace with actual value
AADT increase/year (%) | 0.48% | Derived from HGAC model. Use future year to calculate growth rate. Replace with actual value
Travel time during construction (hours) | 0.12857 | Calculated from the speed limit * length of roadway * doubling travel time. Doubling value decided on at meeting 7/17

## Construction costs
Construction costs used in these analyses
Project Alternative | Unit Cost ($)
| 30287300 | Obtain from PM, do not calculate
Concrete Base Repair
Concrete Base Repair (square yard) | 205 | Assume each panel is 50' * 12' = 67 SY so $13,735/panel
1 Square foot = 0.11111 square yard | 0.11111
Percent of concrete base needing repair | 10% | Replace with field observation or PM information
Mill and Overlay for Asphalt
Mill and Overlay Cost ($/lane mile) | 174640 | TxDOT low bid, 6/30/17. See DR email, 7/19/27
https://www.houstontx.gov/council/committees/tti/20140513/Maintaining_Houston_Streets.pdf

## SOGR and User Costs
(All costs in $2017 base year dollars)
Reconstruction Costs
Removing concrete base and new pavement (concrete):
2020 | 30287300 | Can just replace this with the cost of the project
2030
2040 | -15143650 | This assumes half life left in 2040 (no inflation)
User costs:
2020 | 27624837.9469 | Assumes AADT growth from 2015-2020 and wage increase
Repair Costs
Concrete Base Repair: | [5 empty] | User costs:
2020 | 1451390.0149 |  |  |  |  | 2020 | 6906746.2779 | Assumes AADT growth from 2018-2020 and wage increase
2035 | 2196245.3289 | One more round of repairs in 2035, includes 2.8% inflation |  |  |  | 2035 | 8875147.6277 | Assumes AADT growth from 2018-2035 and wage increase
2040 | -1464163.5526 | Assumes 2/3 of value left in 2040 (no inflation)
Mill and Overlay: | [5 empty] | User costs:
2020 | 1915975.44 |  |  |  |  | 2020 | 6906746.2779 | Assumes AADT growth from 2018-2020 and wage increase
2030 | 2525347.1323 | Includes a 2.8% inflation rate for the 10 years |  |  |  | 2030 | 8163471.6953 | Assumes AADT growth from 2018-2030 and wage increase
2040 | 3328528.1249 | Inflated cost of another round of repairs in 2040 |  |  |  | 2040 | 9648866.1141 | Assumes AADT growth from 2018-2040 and wage increase
Summary Costs ($2017)
| Alternative A: Reconstruct/Project |  | Alternative B: Repair/Non-Project |  | Alternative B: Repair/Non-Project
|  |  | CONCRETE |  | MILL AND OVERLAY
| Construction | User Cost | Construction | User Cost | Construction | User Cost
2020 | 30287300 | 27624837.9469 | 1451390.0149 |  | 1915975.44 | 6906746.2779
2030 | 0 |  |  |  | 2525347.1323 | 8163471.6953
2035 |  |  | 5490613.3223 | 8875147.6277
2040 | -15143650 |  | -3660408.8815
Note: If you only use one treatment, delete out the values in this summary table here (cells 26 down)
Note on F28: Author: Removed user cost will be inclued in M&L
Note on E30: Author: Hard coded in - assummed a 25% replacement in 2035
Note on E31: Author: Hard coded in - assummed a 25% replacement in 2035

## Discounted Costs
Summary Costs ($2017) | [6 empty] | (Not discounted)
| Alternative A: Reconstruct/Project |  | Alternative B: Repair/Non-Project |  | Alternative B: Repair/Non-Project
|  |  | CONCRETE |  | MILL AND OVERLAY
| Construction | User Cost | Construction | User Cost | Construction | User Cost
2020 | 30287300 | 27624837.9469 | 1451390.0149 | 0 | 1915975.44 | 6906746.2779
2030 | 0 | 0 | 0 | 0 | 2525347.1323 | 8163471.6953
2035 | 0 | 0 | 5490613.3223 | 8875147.6277 | 0 | 0
2040 | -15143650 | 0 | -3660408.8815 | 0 | 0 | 0
Total | 15143650 | 27624837.9469 | 3281594.4556 | 8875147.6277 | 4441322.5723 | 15070217.9731
SOGR BENEFIT
31668282.6288 | Repair costs only
-11100205.3181 | Delta between repair and reconstruct scenario
3% Discount Rate | [6 empty] | 3% | Discount Rate
| Alternative A: Reconstruct/Project |  | Alternative B: Repair/Non-Project |  | Alternative B: Repair/Non-Project
|  |  | CONCRETE |  | MILL AND OVERLAY
| Construction | User Cost | Construction | User Cost | Construction | User Cost
2020 | 29405145.6311 | 26820231.0164 | 1409116.5193 | 0 | 1860170.3301 | 6705578.9106
2030 | 0 | 0 | 0 | 0 | 1879095.4342 | 6074389.6129
2035 | 0 | 0 | 3524215.7595 | 5696619.5398 | 0 | 0
2040 | -8384671.8349 | 0 | -2026679.6481 | 0 | 0 | 0
Total | 21020473.7962 | 26820231.0164 | 2906652.6306 | 5696619.5398 | 3739265.7643 | 12779968.5234
SOGR BENEFIT
25122506.4581 | Repair costs only
-22718198.3545 | Delta between repair and reconstruct scenario
7% Discount Rate | [6 empty] | 7% | Discount Rate
| Alternative A: Reconstruct/Project |  | Alternative B: Repair/Non-Project |  | Alternative B: Repair/Non-Project
|  |  | CONCRETE |  | MILL AND OVERLAY
| Construction | User Cost | Construction | User Cost | Construction | User Cost
2020 | 28305887.8505 | 25817605.5579 | 1356439.2662 | 0 | 1790631.2523 | 6454903.0634
2030 | 0 | 0 | 0 | 0 | 1283758.4271 | 4149895.0576
2035 | 0 | 0 | 1990050.9441 | 3216761.9314 | 0 | 0
2040 | -3913406.932 | 0 | -945919.2131 | 0 | 0 | 0
Total | 24392480.9185 | 25817605.5579 | 2400570.9972 | 3216761.9314 | 3074389.6794 | 10604798.1211
SOGR BENEFIT
19296520.7292 | Repair costs only
-30913565.7472 | Delta between repair and reconstruct scenario