## Sheet1
"EXHIBIT C" - Compensation for Professional Services
Project Name: Reconstruction of Sheldon Road from Jacintoport to Market
Project Limits: Jacintoport to Market Street
UPIN: 19102MF0ZC01
Construction Cost Estimate: $16,600,270
1 | Pre-Design Phase
444119
2 | Design Phase
499633
3 | Bid Phase
166545
4 | Survey
|  | Existing ROW Maps and Control | 39204
|  | Topographic Survey | 70329
|  | Level B SUE | 21900
|  | Survey Coordination | 10953
142386
5 | Geotechnical Report
|  | Roadway | 35954
|  | Bridge | 45000
|  | Geotechnical Coordination | 8095
89049
6 | Environmental
|  | Categorical Exclusion | 15000
|  | Environmental Site Assessment (Phase I) | 7745
|  | Wetlands Determination & Delineation | 14400
|  | USGC Permitting | 7745
|  | General Permit | 15000
|  | Cultural Resources - Screening Level Survey | 1650
|  | Threatened & Endangered Species | 4425
|  | Environmental Coordination | 6596.5
72561.5
7 | Drainage
|  | Drainage Report | 35000
|  | Bridge Conveyance Impact Analysis | 5500
|  | CLOMR | 6500
|  | Drainage Coordination | 3200
50200
8 | Traffic
|  | Traffic Signal Design (Sheldon at Market) | 25000
|  | Traffic Signal Modification (Sheldon at Jacintoport) | 12000
|  | Traffic Signal Coordination | 3700
40700
Subtotal Basic Services (1-8): |  |  |  | 1505193.5
9 | Optional Additional Services
(amounts shown are estimates and will be paid according to the Engineer's Rates, unless otherwise identified as Firm Fixed Fee)
|  | Change to Drawings | 35000
|  | Pedestrian Survey (Shovel Testing) | 15000
|  | Individual Permit | 49785
|  | Environmental Site Assessment (Phase II) | 25000
|  | Right-of-Way Mapping - 4 Parcel @ $7,500 | 30000
|  | Additional TxDOT NEPA Scope | 40000
|  | Level A SUE - 15 Test Holes @ $1,500 | 30000
224785
TOTAL SERVICES (BASIC & OPTIONAL ADDITIONAL) | Total Services |  |  | 1729978.5
|  |  | Pre-Design Total | 798315.5
|  |  | Design Total | 931663
|  |  | Combined Total | 1729978.5