## Project Budget - Major Invest
Project Expenditures | Fiscal Year (Sept 1 - Aug 31) | [9 empty] | Project Total
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
Planning/Environmental |  | 500000 | [8 empty] | 500000
Design |  | 1500000 | 1500000 | 1000000 | [6 empty] | 4000000
Property/ROW Acquisition | [10 empty] | 0
Utility Relocation | [10 empty] | 0
Construction Phase 1 |  |  |  |  | 10000000 | 15000000 | 20000000 | 15000000 | 6147113 |  | 66147113
Construction Phase 2 | [10 empty] | 0
Other | [10 empty] | 0
Total Expenditures | 0 | 2000000 | 1500000 | 1000000 | 10000000 | 15000000 | 20000000 | 15000000 | 6147113 | 0 | 70647113
| 14500000 |  |  |  |  | 56147113
Project Funding
Local - Bond |  | 2000000 | 1500000 | 1000000 | 2000000 | 3000000 | 4000000 | 3000000 | 1229422.6 |  | 17729422.6
Local - General Revenue | [10 empty] | 0
Local - Private Contributions | [10 empty] | 0
TxDOT - Other | [10 empty] | 0
Other | [10 empty] | 0
REQUESTED (H-GAC/TxDOT) |  | 0 | 0 | 0 | 8000000 | 12000000 | 16000000 | 12000000 | 4917690.4 |  | 52917690.4
Total Funding | 0 | 2000000 | 1500000 | 1000000 | 10000000 | 15000000 | 20000000 | 15000000 | 6147113 | 0 | 70647113
| 14500000 |  |  |  |  | 56147113

## TXDOT PE COST BREAKDOWN
Highway: | Old Conroe/Magnolia Road
County: | Montgomery
CSJ:
Filename:
Description: | New location 49' curb and gutter
Limits: | FM 1488 to LP 336
Length: | 5.9 miles
Estimate By:
Date: | 2014-12-30
ITEM | DESCRIPTION | UNITS | EST. QTY. | 12/14 UNIT COST | AMOUNT
Roadway
1 | Reconstruction
| 2 Lane Rural Section w/ 8' Shoulders (Flexible Structure) | MI | 0 | 2008913.49 | 0
| 2 Lane Curb & Gutter Frontage Road Section (1 Direction) | MI | 0 | 2990540.82 | 0
| 3 Lane Rural Section without Shoulders | MI | 0 | 1976261.91 | 0
| 3 Lane Curb & Gutter Frontage Road Section (1 Direction) | MI | 0 | 3787510.71 | 0
| 4 Lane Undivided Rural Section w/10' Concrete Shoulders | MI | 0 | 3900996.66 | 0
| 4 Lane Undivided Rural Section w/10' Asphalt Shoulders | MI | 0 | 3917268.33 | 0
| 4 Lane Divided Rural Section w/ 10' Concrete Shoulders (16' Flush Median) | MI | 0 | 4723624.35 | 0
| 4 Lane Divided Rural Section w/10' Asphalt Shoulders (16' Flush Median) | MI | 0 | 4739894.79 | 0
| 4 Lane Divided Curb & Gutter Section (16' Flush Median) | MI | 5.46 | 5993595.66 | 32725032.3036
| 6 Lane Divided Rural Section w/ 10' Concrere Shoulder (16' Flush Median) | MI | 0 | 5957565.27 | 0
| 6 Lane Divided Curb & Gutter Section (13' Raised Median) | MI | 0 | 8426785.35 | 0
| 8 Lane Divided Rural Section w/ 10' Concrete Shoulders (16' Flush Median) | MI | 0 | 7191506.19 | 0
| 8 Lane Divided Curb & Gutter Section (16' Raised Median) | MI | 0 | 10176028.62 | 0
| 10 Lane Freeway Mainlane Section (No Frontage Roads) | MI | 0 | 9336542.55 | 0
| 10 Lane Freeway Mainlane Section w/ 1 Lane HOV (No Frontage Roads) | MI | 0 | 10955227.47 | 0
| 10 Lane Freeway Mainlane Section w/ 2 Lane HOV (No Frontage Roads) | MI | 0 | 11505904.62 | 0
| 12 Lane Freeway Mainlane Section (No Frontage Roads) | MI | 0 | 10658168.94 | 0
| 12 Lane Freeway Mainlane Section w/ 2 Lane HOV (No Frontage Roads) | MI | 0 | 12810184.32 | 0
| 14 Lane Freeway Mainlane Section (No Frontage Roads) | MI | 0 | 11979795.33 | 0
2 | Subgrade Widening
| 1-'12 Lane w/ 10' Shoulder Widening for Concrete Pavement (No New ROW) | MI | 0 | 1154040.12 | 0
| Existing 2-Lane Rural Section w/ 10' Shoulder Widening/Overlay (No ROW) | MI | 0 | 1225269.42 | 0
3 | Ret Walls, Sound Walls & Bridges
| Retaining Wall (Reinforced or Retained Earth) | SF | 0 | 49.2 | 0
| Retaining Wall (Cast-in-Place) | SF | 0 | 61.5 | 0
| Retaining Wall (Soil Nail) - Includes Soil Nails + Facia | SF | 0 | 61.5 | 0
| Retaining Wall (Drill Shaft) - Includes Wall + Drill Shafts | SF | 0 | 184.5 | 0
| Sound Walls (See Itemized List) |  |  | 0
| Bridge Pre-Stressed Concrete I-Beam | SF | 119600 | 61.5 | 7355400
| Bridge Pre-Stressed Concrete U-Beam | SF | 0 | 67.65 | 0
| Bridge Pre-Stressed Concrete Box Beam | SF | 0 | 79.95 | 0
| Bridge Pre-Stressed Concrete Slab Beam | SF | 0 | 98.4 | 0
| Bridge Steel Plate Girder | SF | 0 | 147.6 | 0
| Bridge Steel Trapezoidal Box Girder | SF | 0 | 196.8 | 0
4 | Prep ROW and Remove Conc, Asph, Base & Curb
| Prep ROW | AC | 72 | 22140 | 1594080
| Prep ROW (Small Project) | STA | 0 | 6150 | 0
| Prep ROW (Medium Project) | STA | 0 | 12300 | 0
| Prep ROW (Large Project) | STA | 0 | 32595 | 0
| Remove Concrete (Pavement) | SY | 0 | 7.38 | 0
| Remove Concrete (Curb) | LF | 0 | 6.15 | 0
| Remove Stab Base and/or Asphalt Pav (Var Depth) | SY | 0 | 7.38 | 0
| Remove Structures (Bridge) (0' - 99') | EA | 0 | 14760 | 0
| Remove Structures (Bridge) (100' - 499') | EA | 0 | 92250 | 0
| Remove Structures (Bridge) (500' - 999') | EA | 0 | 123000 | 0
| Remove Structures (Box Culvert) | LF | 0 | 36.9 | 0
| Remove Structures (Pipe Culvert) | LF | 0 | 24.6 | 0
5 | Pump Stations
| Pump Station - Rehab of Existing | CFS | 0 | 14760 | 0
| Pump Station - New | CFS | 0 | 22140 | 0
6 | Traffic Barrier & Guard Fence
| Metal Beam Guard Fence (Ty II) (Timber Post) | LF | 0 | 43.05 | 0
| Concrete Traffic Barrier (Furnish & Install) | LF | 0 | 55.35 | 0
| Guardrail End Treatment (Inst) (Wood Post) (Ty II) | EA | 0 | 3444 | 0
| Crash Cushion Attenuator (Install) (REACT) (N) | EA | 0 | 36900 | 0
7 | Signing, Lighting & Pavement Markings
| Signing Freeway - Major/Minor Interchanges | PAIR | 0 | 492000 | 0
| Signing Freeway - Mainlanes | MI | 0 | 24600 | 0
| Signing Frontage Roads Both Sides | MI | 0 | 30750 | 0
| Signing Other Roadways | MI | 5.9 | 30750 | 181425
| High Mast Continuous 100' Mounting Height | MI | 0 | 615000 | 0
| High Mast Continuous 125' Mounting Height | MI | 0 | 725700 | 0
| High Mast Continuous 150' Mounting Height | MI | 0 | 793350 | 0
| High Mast Continuous 175' Mounting Height | MI | 0 | 869610 | 0
| Conventional Median Lights (8 Ft. Dbl Arm) (H=38 Ft.) | MI | 0 | 199260 | 0
| Conventional Both Sides Lights (10 Ft. Arm) (H=40 Ft.) | MI | 0 | 444030 | 0
| Conventional One Side Lights (10 Ft. Arm) (H=40 Ft.) | MI | 0 | 222630 | 0
| Conventional Median Lights (8 Ft. Dbl Arm) (H=50Ft.) | MI | 0 | 209100 | 0
| Conventional Both Sides Lights (10 Ft. Arm) (H=50 Ft.) | MI | 0 | 479700 | 0
| Contentional One Side Lights (10 Ft. Arm) (H=50 Ft.) | MI | 0 | 239850 | 0
| Safety - Underpass (Ty 1) (High Presure Sodium) | EA | 0 | 33210 | 0
| Safety - Underpass (Induction Flouresent) | EA | 0 | 38130 | 0
| Entry/Exit Ramp (per Ramp) | EA | 0 | 41820 | 0
| Striping Freeway 8 Lanes | MI | 0 | 307500 | 0
| Striping Freeway 6 Lanes | MI | 0 | 246000 | 0
| Striping Freeway 4 Lanes | MI | 0 | 215250 | 0
| Striping Rural Frontage Road - Both Sides - 3 Lanes | MI | 0 | 36900 | 0
| Striping Rural Frontage Road - Both Sides - 2 Lanes | MI | 0 | 31980 | 0
| Striping Rural 4 Lane - 2 Way Roadways | MI | 5.9 | 36900 | 217710
| Striping Rural 2 Lane - 2 Way Roadways | MI | 0 | 27060 | 0
8 | Traffic Signals & Computerized Traffic Management
| Single Intersection - Strain Poles | Per Int | 0 | 159900 | 0
| Single Intersection - Mast Arms | Per Int | 0 | 196800 | 0
| Diamond Interchange - Strain Poles | Per Int | 0 | 184500 | 0
| Diamond Interchange - Mast Arms | Per Int | 2 | 246000 | 492000
| CTMS - Conduit | MI | 0 | 307500 | 0
| CTMS - Devices | MI | 0 | 246000 | 0
9 | Storm Drains & Ponds
| Freeway Mainlanes & Frontage Roads | MI | 0 | 2952000 | 0
| Urban Roadway - 4 Lane Curb & Gutter w/ CLT | MI | 5.9 | 1968000 | 11611200
| Urban Roadway - 6 Lane Curb & Gutter w/ CLT | MI | 0 | 3198000 | 0
| Rural Roadway - 2 Lane w/ Shoulders & Open Ditches | MI | 0 | 590400 | 0
| Rural Roadway - 4 Lane w/ Shoulders & Open Ditches | MI | 0 | 959400 | 0
| Detention Pond * | AC-FT | 0 | 61500 | 0
| Inline Detention System (10' x 10' Box Culvert) * | MI | 0 | 6494400 | 0
* When considering Inline Detention vs. Detention Pond, also take into account the cost of ROW
10 | Miscellaneous Items
| Americans w/ Disabilities Act (ADA) Features | MI | 0 | 246000 | 0
Stormwater Pollution Prevention Plan (SW3P)
| Major | MI | 5.9 | 76260 | 449934
| Minor | LS | 0 | 3075 | 0
Temporary Structures
| Roadway | SF | 0 | 86.1 | 0
| Railroad | SF | 0 | 123 | 0
11 | Additional Items
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  |  | SUBTOTAL | 54626781.3036
12 | Landscaping - Baseline Including Plant Material | SF | 0 | 1.845 | 0
| Complete w/ Irrigation | SF | 0 | 3.075 | 0
13 | Mobilization | LS | 1 | 10.11% | 5462678.1304
14 | Premium Charged for Accelerated / Special Projects or Projects w/ Confined Work Areas | LS | 0 | 10.11% | 0
15 | Traffic Control (TCP)
| Complex Projects (Fwy Reconstruction) | MO | 0 | 49200 | 0
| Major Projects (Fwy Construction) | MO | 0 | 30750 | 0
| Intermediate Projects (4 & 6 Lane) | MO | 0 | 18450 | 0
| Minor Projects (Simple Rdwy Reconstruction) | MO | 0 | 6150 | 0
| Minimal Projects (Simple Rdwy Construction or Rehab) | MO | 0 | 3690 | 0
| New Location Projects (Rdwy Construction on New Location) | MO | 24 | 1845 | 44280
|  |  |  | TOTAL | 60133739.434
16 | Contingency
|  | LS | 1 | 10% | 6013373.9434
|  |  |  | GRAND TOTAL | 66147113.3774

## Project Budget - Other Invest
Project Expenditures ('000s) | Project Total
Planning/Environmental
Design
Property/ROW Acquisition
Utility Relocation
Construction
Other
Total Expenditures | 0
Project Funding ('000s)
Local - Bond
Local - General Revenue
Local - Private Contributions
TxDOT - Other
Other
REQUESTED (H-GAC/TxDOT)
Total Funding | 0

## Operating¦Maintenance Budget
Operating/Maintenance Expenditures ('000s) | Fiscal Year (Sept 1 - Aug 31) |  |  |  |  | Project Total
| 2018 | 2019 | 2020 | 2021 | 2022
0
0
0
0
0
0
0
Total Expenditures | 0 | 0 | 0 | 0 | 0 | 0
0
Revenues ('000s)
0
0
0
0
0
REQUESTED (H-GAC/TxDOT) | [5 empty] | 0
Total Revenues | 0 | 0 | 0 | 0 | 0 | 0
0
1st Year of Operations